## Cover
PLF-ECMS REGRESSION TEST CASES
Version:	1.6
Issue date:	10-Aug-12
Project Suite:
Project Name:	ECMS
Total Cases:	92
Test Status:	Passed: Test is OK Blocked: Could not run the test (another bug is blocking) Failed: Test failed, a bug is entered on it (please add the bug ID) N/A: Test is not possible to run on this version
Record of change:
Effective Date	Version	Change description	Originator	Reviewer/ / Approver	Reference
	1.0	Create test run file	Chau.Tran
Nov-4-11	1.1	Update CheckList, Summary report, CaseNo	Hanh.ly
29-Feb-12	1.2	Add Sheet Bugs_v2_1_8	Ha.Khuat
25-May-12	1.3	Add Sheet Bugs_v2_1_9	Hanh.ly
24-Jul-12	1.4	Update testcase base on feedback of TC 3.5.4	Hanh.ly
6-Aug-12	1.5	Update testcase for new sheet: XSS	Hanh.ly
10-Aug-12	1.6	Add Sheet Bugs_v2_1_10	Hanh.ly
30-Aug-12	1.7	Update testcase base on feedback of TC 3.0.10	Hanh.ly

## Check_List
Check List / Based on Product built version:ECMS 2.1.x	Check List / Based on Product built version:	Check List / Based on Product built version:	Check List / Based on Product built version:	Check List / Based on Product built version:
Id	Main cases	Priority	Selenium	Table of record
Bugs_v2_1_4				Total of High	0
REG_PLF304_ECMS_001.001	Check life cycle in Manage Publications	High		Total of Medium	0
REG_PLF304_ECMS_002.001	Check Category validation	High		Total of Low	0
REG_PLF304_ECMS_003.001	Check rss with special characters	High
REG_PLF304_ECMS_004.001	Download attachment in Content Detail portlet	High
REG_PLF304_ECMS_005.001	Check Content by URL page in public	High
REG_PLF304_ECMS_006.001	Check Page Navigation in WCM Content Selector	High
REG_PLF304_ECMS_007.001	Check multi-value WISIWYG field	High
Bugs_v2_1_5
REG_PLF305_ECMS_001.001	Check Portuguese language translation of document	High
REG_PLF305_ECMS_002.001	Check Duplicity Content Filter in CLV	High
REG_PLF305_ECMS_003.001	Edit HTML in Content Explorer	High
REG_PLF305_ECMS_004.001	Upload illustration image in free layout web content	High
REG_PLF305_ECMS_005.001	Check form Select Category	High
REG_PLF305_ECMS_006.001	Check long comment readability	High
REG_PLF305_ECMS_007.001	Adding image in a content from CLV	High
REG_PLF305_ECMS_008.001	Publish document in a locked folder	High
REG_PLF305_ECMS_009.001	Check returned URL when navigated back to a CLV page after editing in Content Explorer	High
REG_PLF305_ECMS_010.001	Check French Translation in Newsletter	High
REG_PLF305_ECMS_011.001	Check French Translation in Content Explorer	High
REG_PLF305_ECMS_012.001	Check WCM Content Selector in Chrome	High
REG_PLF305_ECMS_013.001	Check FCK Editor in Chrome	High
REG_PLF305_ECMS_014.001	Inject java script	High
REG_PLF305_ECMS_015.001	Check multi value flag in View Node Properties	High
REG_PLF305_ECMS_016.001	Upload a pdf file with user-input name	High
REG_PLF305_ECMS_017.001	Manage Publications	High
Bugs_v2_1_6
REG_PLF306_ECMS_001.001	Check limit of taxonomy length	High
REG_PLF306_ECMS_002.001	Check RTF Document Edition Dialog	High
REG_PLF306_ECMS_003.001	Check server start-up with specified language	High
REG_PLF306_ECMS_004.001	Check permission removal on document	High
REG_PLF306_ECMS_005.001	Edit metadata with multi-value	High
REG_PLF306_ECMS_006.001	Search and download file of which name contain apostrophe ( character ' )	High
REG_PLF306_ECMS_007.001	Check page navigation in File Explorer	High
REG_PLF306_ECMS_008.001	Check content sort order in CLV	High
REG_PLF306_ECMS_009.001	Check Portuguese translation	High
REG_PLF306_ECMS_010.001	Check Edit form of a File document	High
REG_PLF306_ECMS_011.001	Check link in WYSIWYG field	High
REG_PLF306_ECMS_012.001	Check 'Add Translation' with Simplified Chinese	High
REG_PLF306_ECMS_013.001	Check Space Document	High
REG_PLF306_ECMS_014.001	Check Group drives	High
REG_PLF306_ECMS_015.001	Check Manage Publication Panel template	High
Bugs_v2_1_7
REG_PLF307_ECMS_001	"View Properties" Component	High
REG_PLF307_ECMS_002	Replacing a file in categories	High
REG_PLF307_ECMS_003	Selecting the 'workflow' publication workflow	High
REG_PLF307_ECMS_004	Images in ACME Site	High
REG_PLF307_ECMS_005	*, ~, +, - characters in simple search and advanced search	High
REG_PLF307_ECMS_006	Linked documents of article is click-able in a SCV page	High
REG_PLF307_ECMS_007	Check the displaying of Content based on custom node type a CLV page	High
REG_PLF307_ECMS_008	Check right URL when in put title of node with specical characters in IE 7 and IE 8	High
REG_PLF307_ECMS_009	Check search result with keyword in comment of document	High
REG_PLF307_ECMS_010	Check the displaying of Content explorer portlet in 'level3' page	High
REG_PLF307_ECMS_011	Check that Double left click on a node works properly in Chrome	Medium
REG_PLF307_ECMS_012	Check delete Favorites folder in Private Drive of user	Medium
REG_PLF307_ECMS_013	Check "Add/Manage Content" actions from CLV in "Dynamic Navigation" active mode	Medium
REG_PLF307_ECMS_014	Check load icon in Simple View	Medium
REG_PLF307_ECMS_015	Check java.util.MissingResourceException when try to open a PDF file.	Medium
REG_PLF307_ECMS_016	Check: delete a node of a workspace different from trash one's	Medium
REG_PLF307_ECMS_017	Check: Shared css and js is reloaded after server restart	Medium
REG_PLF307_ECMS_018	A node that don't point to a page does not have a link on Navigation portlet	Medium
REG_PLF307_ECMS_019	Setting a content Explorer with parameterize option	Medium
Bugs_v2_1_8
REG_PLF308_ECMS_001	Check whether unknown error appears when do action on document while trying to edit	High
REG_PLF308_ECMS_002	Create and delete javascript files from Content Explorer	High
REG_PLF308_ECMS_003	Check name is automatically generated when creating a new content	High
REG_PLF308_ECMS_004	Check whether Uploaded image gets overwritten	High
REG_PLF308_ECMS_005	Check Search results are displayed 10 items per page	High
REG_PLF308_ECMS_006	Check displaying of Content Explorer portlet in home page	High
REG_PLF308_ECMS_007	Click on "View document" in a space	High
REG_PLF308_ECMS_008	Check applying two filters in the Filter By Type of File Explorer	High
REG_PLF308_ECMS_009	Check the results of an initial research is cleared during a second search	High
REG_PLF308_ECMS_010	Searching under a category in Sites Explorer	Medium
REG_PLF308_ECMS_011	Check nullPointerException when Setting a name to taxonomyAction	Medium
REG_PLF308_ECMS_012	Check displaying HTM Lists in exo content.	Medium
REG_PLF308_ECMS_017	Check Hidden Field's value is reset when editing a document	Medium
Bugs_v2_1_9
REG_PLF309_ECMS_001	Check XSS with Navigation on URL	High
REG_PLF309_ECMS_002	Check the displaying of content in CLV portlet	High
REG_PLF309_ECMS_003	Check XSS in Search portlet	High
REG_PLF309_ECMS_004	Check default value of Calendar field	High
REG_PLF309_ECMS_005	Add new webcontent with java script	High
REG_PLF309_ECMS_006	Filter some actions insite nt: file	High
REG_PLF309_ECMS_007	Check webDAV link	High
REG_PLF309_ECMS_008	Printing PDF	High
REG_PLF309_ECMS_009	Check thumbnail view of PDF file	Medium
REG_PLF309_ECMS_010	Check footer in IE9	Medium
REG_PLF309_ECMS_011	Check the SignIn portlet after edit	Medium
Bugs_v2_1_9
REG_PLF3010_ECMS_001	Delete content with accented name	High
REG_PLF3010_ECMS_002	Copy large files	High
REG_PLF3010_ECMS_003	Download file	High
XSS
REG_PLF309_ECMS_001	XSS vulnerability in tag's style	High
REG_PLF309_ECMS_002	XSS vulnerability in Documents feature	High
REG_PLF309_ECMS_003	Inject java script in Contact Us form	High

## Bugs_v2_1_4
	TEST CASES					Passed	0	0	0	0
				Failed	0	0	0	0
	Function List:	Bugs on ECMS 2.1.6 for regression test					Blocked	0	0	0	0
	Total Main Cases:	7					Untested	0	0	0	0
				N/A	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
1.00	REG_PLF304_ECMS_001	1.00	REG_PLF304_ECMS_001	Check life cycle in Manage Publications	Step 1: Select a document is not enrolled	- Go to Content Explorer, Sites Management/acme/documents / - Select a document which is not enrolled (should use any of default documents in Web contents folder)	Document is opened	High	ECMS-1907 / CCP-625	Authoring lifecycle is always used.
	REG_PLF304_ECMS_001	1.00	REG_PLF304_ECMS_001	Check life cycle in Manage Publications	Step 2: Select another lifecycle other than Authoring	- Click Manage Publications. In condition the document is not enrolled, a pop-up will show to select lifecycle: / + Workflow / + States and versions based publication / + Authoring publication / - Click to select any lifecycle except “Authoring publication” / Note: If you choose Workflow you have to config to run workflow before starting server, otherwise exception will be thrown out	The pop-up Manage Publications displays selected lifecycle, not Authoring fifecycle. / (If Authoring life cycle, you will see status Draft → Pending → Approved → Staged → Published	High
2.00	REG_PLF304_ECMS_002	1.00	REG_PLF304_ECMS_002	Check Category validation	Step 1: Modify dialog of template “File”	- Go to Site Administration → Content Presentation → Manage Templates / - Click Edit icon of nt:file template / - Select Dialog tab / - Click Edit icon of dialog1 and replace all its code with code provided here : https://jira.exoplatform.org/secure/attachment/29248/dialog1.txt / - Save	Dialog of nt:file template is edited	High	ECMS-1908 / CCP-739
	REG_PLF304_ECMS_002	1.00	REG_PLF304_ECMS_002	Check Category validation	Step 2: Input invalid category	- Go to Content Explorer / - Create a document, select template File / - Input (typing) field Category which is not existed / - Input all required fields then click Save	A message says that the category is wrong.	High		Category is cleared without message.
3.00	REG_PLF304_ECMS_003	1.00	REG_PLF304_ECMS_003	Check rss with special characters	Step 1: Edit document with special characters	- Go to Content Explorer / - Under Sites Management/acme/web contents/News, edit document / - In the title put special characters (such as %) / - Save and publish this document	Document is edited and published	High	ECMS-1953 / CCP-762	Exception : URLDecoder: Illegal hex characters in escape (%) pattern - For input string: "</"
	REG_PLF304_ECMS_003	1.00	REG_PLF304_ECMS_003	Check rss with special characters	Step 2: Check rss with special characters	- Go to acme homepage / - Click on the rss icon of Lastest News portlet	Content displays well. No exception.	High
4.00	REG_PLF304_ECMS_004	1.00	REG_PLF304_ECMS_004	Download attachment in Content Detail portlet	Step 1: Create a document	- Log in as root / - Go to Content Explorer / - Go to Sites Management/acme/web contents/Events / - Create 1 Article document	The article is created successfully	High	ECMS-1980 / CCP-776
	REG_PLF304_ECMS_004	1.00	REG_PLF304_ECMS_004	Download attachment in Content Detail portlet	Step 2: Create attach file for document	- Select Article document above / - Click Upload icon in action bar / - Select a pdf file to attach to the article	File is attached for document	High
	REG_PLF304_ECMS_004	1.00	REG_PLF304_ECMS_004	Download attachment in Content Detail portlet	Step 3: Publish file	- Select Article document and publish / - Select uploaded file and publish	Both Article document and PDF file are published	High
	REG_PLF304_ECMS_004	1.00	REG_PLF304_ECMS_004	Download attachment in Content Detail portlet	Step 4: Download attachment in Content Detail portlet	- Go to site acme, create a page with Content detail portlet / - Choose this article as content / - Open this page / - Click the link of attachment / - Click on download link of this attachment	User can open/download the attachment	High		Unable to open/ download the attachment
5.00	REG_PLF304_ECMS_005	1.00	REG_PLF304_ECMS_005	Check Content by URL page in public, this case run only on ECMS standalone	Step 1: Create 2 documents	- Login / - Go to Content Explorer, create and publish 2 documents (content1, content2)	2 documents are created and published	High	ECMS-1981 / CCP-777
	REG_PLF304_ECMS_005	1.00	REG_PLF304_ECMS_005	Check Content by URL page in public, this case run only on ECMS standalone	Step 2: Create Content by URL page	- Create a page under acme home page / - Create a new page and add Content by URL portlet / - Configure portlet: / + in Content Selection select "content1" / + go to --> Advanced -->Dynamic Navigation, in Contextual Content select Enabled and make the value by "path") / - Save / - Logout (to view the page in public mode as anonymous)	- New page with Content by URL is created / - User logs out	High
	REG_PLF304_ECMS_005	1.00	REG_PLF304_ECMS_005	Check Content by URL page in public, this case run only on ECMS standalone	Step 3: View content in public mode	- Open the page and point the portlet to content1 by passing the path of the content in the URL. / ex: http://localhost:8080/ecmdemo/page?path=/repository/collaboration/sites content/live/acme/content1 / - In second tab of the browser, open the page with path parameter pointing to the second content. / ex: http://localhost:8080/ecmdemo/page?path=/repository/collaboration/sites content/live/acme/content2 / - Wait for a moment (5 to 10 seconds) / - Reload tab1 and tab2 multiple times	The right contents are always displayed.	High		You will see that data of content1 URL is shown in the page of content2 and vice versa.
6.00	REG_PLF304_ECMS_006	1.00	REG_PLF304_ECMS_006	Check Page Navigation in WCM Content Selector	Step 1: Prepare many image documents	- Go to Content Explorer / - In a folder, upload many image files (you can upload one then copy/ paste) so that the folder has many pages	Image files are uploaded successfully	Medium	ECMS-2000 / CCP-794
	REG_PLF304_ECMS_006	1.00	REG_PLF304_ECMS_006	Check Page Navigation in WCM Content Selector	Step 2: Open WCM Content Selector	- Create an article/ Free layout web content / - In main content FCK Editor, click icon Insert Content Link to open this windows	Content Selector window is opened to select content	Medium	ECMS-2000 / CCP-794
	REG_PLF304_ECMS_006	1.00	REG_PLF304_ECMS_006	Check Page Navigation in WCM Content Selector	Step 3: Test pagination	- In Content Selector windows, navigate to the folder of step 1. Its content will be displayed in right pane. / - Verify that the pagination (page 1, page 2, next page, previous page, …) works	Pagination works normally	Medium	ECMS-2000 / CCP-794	In Chrome and IE7, the page navigation is not visible (partly)
	REG_PLF304_ECMS_006	1.00	REG_PLF304_ECMS_006	Check Page Navigation in WCM Content Selector	Step 4: Test pagination with filter	- In Content Selector, on filter box select Medias / - Again verify the pagination	Pagination works normally	Medium	ECMS-2000 / CCP-794	In Chrome and IE7, the page navigation is not visible (partly)
7.00	REG_PLF304_ECMS_007	1.00	REG_PLF304_ECMS_007	Check multi-value WISIWYG field	Step 1: Prepare (download) some necessary files	- Download https://jira.exoplatform.org/secure/attachment/31278/multivalued_wysiwyg.zip / - Extract this file, there will be nodetype.xml inside	File is downloaded successfully	High	ECMS-2009 / CCP-801
	REG_PLF304_ECMS_007	1.00	REG_PLF304_ECMS_007	Check multi-value WISIWYG field	Step 2: Import Nodetype	- Go to Content Administration/ Content Types / Manage Node Type / - Import nodetype.xml	New nodetype exo:test is imported successfully, and listed in Node type list	High	ECMS-2009 / CCP-801
	REG_PLF304_ECMS_007	1.00	REG_PLF304_ECMS_007	Check multi-value WISIWYG field	Step 3: Change template	- Go to Content Presentation/ Manage Template / - Click Add and select name as exo:test, Fill lable, choose permission / - Go to dialog tab, copy content from multivaluedWysiwyg_dialog.gtmpl to dialog tab and save.	New template is created successfully	High
	REG_PLF304_ECMS_007	1.00	REG_PLF304_ECMS_007	Check multi-value WISIWYG field	Step 4: Create a document	- Go to Content Explorer / - Create a new document with the above template / - Add many values to body field / - Save	Document with new template is created	High
	REG_PLF304_ECMS_007	1.00	REG_PLF304_ECMS_007	Check multi-value WISIWYG field	Step 5: Open the document	- Open the document (to view content) and test the body field	All inputed values are well displayed	High	ECMS-2009 / CCP-801	Field Body is empty
	REG_PLF304_ECMS_007	1.00	REG_PLF304_ECMS_007	Check multi-value WISIWYG field	Step 6: Edit the document	- Click 'Edit document' / - Test field body	All inputed values are well displayed	High	ECMS-2009 / CCP-801	Field Body is empty

## Bugs_v2_1_5
	TEST CASES					Passed	0	0	0	0
				Failed	0	0	0	0
	Function List:	Bugs on ECMS 2.1.6 for regression test					Blocked	0	0	0	0
	Total Main Cases:	17					Untested	0	0	0	0
				N/A	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
1.00	REG_PLF305_ECMS_001	1.00	REG_PLF305_ECMS_001	Check Portuguese language translation of document	Step 1: Add language in dialog template	- Go to Content Administration, Manage Templates / - Edit template exo:article / - In Dialog tab, select the existing dialog to edit / - Find a line like this: / String[] fieldLang = ["jcrPath=/node/exo:language", "options=en,fr,es,de", lang] ; / - Add 'pt_BR' to this line: / String[] fieldLang = ["jcrPath=/node/exo:language", "options=en,fr,es,de,pt_BR", lang] ; / - Save template	exo:article is edited with new language	High	ECMS-1913 / CCP-743 / CCP-874
	REG_PLF305_ECMS_001	1.00	REG_PLF305_ECMS_001	Check Portuguese language translation of document	Step 2: Create document with difference language	- Go to Content Explorer / - Open form to add Article document / - Choose language: en / - Fill required fields / - Save / - Do steps above with fr and pt_BR language	- 3 articles in English, French and Portuguese are created	High
	REG_PLF305_ECMS_001	1.00	REG_PLF305_ECMS_001	Check Portuguese language translation of document	Step 3: Add translation for English article	- Select English article document / - Click on Add Translation in action bar (Please add this action to the view that you are using if you don't see it) / - Select French and Portuguese article document	- English article is added translation of French and Portuguese articles	High
	REG_PLF305_ECMS_001	1.00	REG_PLF305_ECMS_001	Check Portuguese language translation of document	Step 4: Add a page to display the document	- Add a new page with Content Detail portlet / - Select en article to be content of the portlet / - Save the page / - Change to Edit mode	New SCV page is displayed in edit mode with content is en article	High
	REG_PLF305_ECMS_001	1.00	REG_PLF305_ECMS_001	Check Portuguese language translation of document	Step 5: Change language to French	- Change language to French and check content display	fr content displays	High
	REG_PLF305_ECMS_001	1.00	REG_PLF305_ECMS_001	Check Portuguese language translation of document	Step 6: Change language to Portuguese – Brazil	- Change language to Portuguese - Brazil and check content display	pt_BR content displays	High		fr content displays well but pr_BR does not
2.00	REG_PLF305_ECMS_002	1.00	REG_PLF305_ECMS_002	Check Duplicity Content Filter in CLV	Step 1: Add Content	- Go to Content Explorer, create a document, eg Article or file …	Content is created	High	ECMS-1939 / CCP-853	Duplicate content.
	REG_PLF305_ECMS_002	1.00	REG_PLF305_ECMS_002	Check Duplicity Content Filter in CLV	Step 2: Add category for document	- Choose this document / - Click Manage categories on action bar / - Select acme category tree / - Choose more than 1 category for this, eg acme/ Movement and acme/Defense	Document is in 2 different categories	High
	REG_PLF305_ECMS_002	1.00	REG_PLF305_ECMS_002	Check Duplicity Content Filter in CLV	Step 3: Create SCV page	- Create a new page with Content List portlet / + Choose by content / + Click on + icon to select folder path, - choose General drives/ Sites management/ acme/ categories/ Movement / - choose General drives/ Sites management/ acme/ categories/ Defense	Warning message appear says that This content is already in the list content.	High
3.00	REG_PLF305_ECMS_003	1.00	REG_PLF305_ECMS_003	Edit HTML in Content Explorer	Step 1: Create a document	- Login as root / - Go to Content Explorer / - Create 1 free layout web-content	Document is created	High	ECMS-1940 / CCP-846	Exception in console/ Unknown error in UI
	REG_PLF305_ECMS_003	1.00	REG_PLF305_ECMS_003	Edit HTML in Content Explorer	Step 2: Edit html document	- Open document above / - Right-click on default.html and select Edit / - In Edit form, edit something / - Click Save as Draft	Save successfully. No exception.	High
4.00	REG_PLF305_ECMS_004	1.00	REG_PLF305_ECMS_004	Upload illustration image in free layout web content	Step 1: Add a web content with illustration	- Go to Content Explorer / - Add a new Free Layout web content "wc1" and fill mandatory fields / - In Illustration tab, upload an illustration image / - Save and close	New free layout webcontent is created	High	ECMS-1995 / CCP-789	In this folder there is an empty image.
	REG_PLF305_ECMS_004	1.00	REG_PLF305_ECMS_004	Upload illustration image in free layout web content	Step 2:Verify illustration	- Select this webcontent / - Go to medias/images/illustration	The uploaded illustration image is located in this folder.	High
5.00	REG_PLF305_ECMS_005	1.00	REG_PLF305_ECMS_005	Check form to Select Category	Step 1: Create a document	- Login and navigate to Site Management/acme/documents in Content Explorer / - Create a document and save	New document is created successfully	High	ECMS-1998 / CCP-791
	REG_PLF305_ECMS_005	1.00	REG_PLF305_ECMS_005	Check form to Select Category	Step 2: Check default category	- Open this document, click Manage Categories / - Select tab Select Category / - Check default taxonomy tree and its sub nodes	By default a taxonomy tree is being selected, and list all its sub nodes to select	High		taxonomy tree 'intranet' is being selected, but its sub nodes do not display. There is 'Child not found' notification.
	REG_PLF305_ECMS_005	1.00	REG_PLF305_ECMS_005	Check form to Select Category	Step 3: Check selective categories	- Change around taxonomy trees and verify sub nodes	Sub nodes are displayed well and available to select	High
6.00	REG_PLF305_ECMS_006	1.00	REG_PLF305_ECMS_006	Check long comment readability	Step 1: Add free layout web content	- Go to Content Explorer / - Add a free layout web content / - Enter a short main content (should only one line) / - Save	Free layout web content is created	Medium	ECMS-2024 / CCP-816
	REG_PLF305_ECMS_006	1.00	REG_PLF305_ECMS_006	Check long comment readability	Step 2: Add a long comment	- Add long comment for the web content / - Save the comment	Comment is saved and is shown below document's content	Medium
	REG_PLF305_ECMS_006	1.00	REG_PLF305_ECMS_006	Check long comment readability	Step 3: Verify if user can read full comment	- Click Show Comment	User can scroll to view full comment	Medium		User has no way to view the whole comment
7.00	REG_PLF305_ECMS_007	1.00	REG_PLF305_ECMS_007	Adding image in a content from CLV	Step 1: Add a free layout web content and an image	- Go to Content Explorer, drive Site management/acme/documents / - Add a free layout web content / - Save	New free layout web content is created	High	ECMS-2072 / CCP-844
	REG_PLF305_ECMS_007	1.00	REG_PLF305_ECMS_007	Adding image in a content from CLV	Step 2: Upload image file in webcontent	- Select created web-content above / - Select 1 file to upload into webcontent	Uploaded file is child node of free layout web content	High
	REG_PLF305_ECMS_007	1.00	REG_PLF305_ECMS_007	Adding image in a content from CLV	Step 3: Add a CLV portlet	- Go to acme site home page / - Add a page with a CLV portlet, add content for it selecting your web content / - Save your page	- New page is created but in publish mode, you can not view content	High
	REG_PLF305_ECMS_007	1.00	REG_PLF305_ECMS_007	Adding image in a content from CLV	Step 4: Edit content	- Switch to edit mode / - Click on icon Edit in Content Explorer / - In main content (FCK Editor), click on “Insert Content Link” icon, a pop-up opens. / - On the pop-up select your image, the image will be inserted into main content / - Double click on image (or right-click and select Properties), a pop-up will show image properties / - Click OK / - Click Save & Close / - There is an “Back” icon on the right, click it to return your CLV page	- Uploaded image is displayed in content of free layout web content / - Go back CLV page	High
	REG_PLF305_ECMS_007	1.00	REG_PLF305_ECMS_007	Adding image in a content from CLV	Step 5: View the image	- Make sure that you are still in Edit mode / - Because your page is a CLV, the content detail will not show. Click on 'Read more' to view the content detail / - Check if the image is displayed	The image is displayed	High		Empty main content
8.00	REG_PLF305_ECMS_008	1.00	REG_PLF305_ECMS_008	Publish document in a locked folder	Step 1: Lock a folder	- Go to Content Explorer / - Go to drive Collaboration, / - Right click on Documents folder and select Lock	Documents folder is locked	Medium	ECMS-2079 / CCP-848
	REG_PLF305_ECMS_008	1.00	REG_PLF305_ECMS_008	Publish document in a locked folder	Step 2: Create a document	- Select the locked folder / - Create a document / - Save & close	New document is created in locked folder	Medium
	REG_PLF305_ECMS_008	1.00	REG_PLF305_ECMS_008	Publish document in a locked folder	Step 3: Click Publish	- Select the created document, click Publish (do not use menu Manage Publication)	The document is published successfully. No exception.	Medium		Exception : / "javax.jcr.lock.LockException: Node /Documents is locked..."
9.00	REG_PLF305_ECMS_009	1.00	REG_PLF305_ECMS_009	Check returned URL when navigated back to a CLV page after editing in Content Explorer	Step 1: Add CLV page	- Login and add a page / - Add a CLV portlet / - Select some contents for the portlet / - Save the page	CLV is created with selected contents	High	ECMS-2088 / CCP-856
	REG_PLF305_ECMS_009	1.00	REG_PLF305_ECMS_009	Check returned URL when navigated back to a CLV page after editing in Content Explorer	Step 2: Send page request with some parameters in URL	Notice that after you save the page, the URL in browser address bar is likely to : http://localhost:8080/portal/private/acme/page100 / - Add following text (2 or more parameters) to the URL : ?a=1&b=2&c=3 / So the URL will be likely to : / http://localhost:8080/portal/private/acme/page100?a=1&b=2&c=3 / - Enter this URL to send page request	The page is displayed again	High	ECMS-2088 / CCP-856
	REG_PLF305_ECMS_009	1.00	REG_PLF305_ECMS_009	Check returned URL when navigated back to a CLV page after editing in Content Explorer	Step 3: Edit content then back to page, check URL	- Switch to Edit mode / - Edit any content (mouse over on the content you want to edit and click on pen icon) / - After edit something, click Save as draft, Close / - There is a 'back' arrow in the left. Click it to return to the page / - Verify the URL in the address bar of your browser	The URL is the same with the URL you send page request before.	High	ECMS-2088 / CCP-856	Parameters are missing except the first one (a=1)
10.00	REG_PLF305_ECMS_010	1.00	REG_PLF305_ECMS_010	Check French Translation in Newsletter	Step 1: Check French translation	- Login / - Go to ACME/Newsletters / - Input email address and Check to subscribe / - Click on Subscribe / - Change language into French	Button “Change Subscriptions” is translated to be “Modifier mon Abonnement”	High	ECMS-2090 / CCP-707	Not translated
11.00	REG_PLF305_ECMS_011	1.00	REG_PLF305_ECMS_011	Check French Translation in Content Explorer	Step 1: Check the translation when right click	- Change language to French / - Login and go to Content Explorer / - Right click on 1 node	'Download and Allow Edition' is changed to 'Télécharger pour édition'	Medium	ECMS-2103 / CCP-861	Some errors in translation
	REG_PLF305_ECMS_011	1.00	REG_PLF305_ECMS_011	Check French Translation in Content Explorer	Step 2: Check the translation in Preferences Setting form	- Click on Setup Preferences icon	- Owned by me → Créés par moi / - Favorites → Favoris / - Hidden → Cachés	Medium
	REG_PLF305_ECMS_011	1.00	REG_PLF305_ECMS_011	Check French Translation in Content Explorer	Step 3: Check the translation in Filter document Type form	- Click on Setup Filter Preferences icon	- Content → Contenu / - Document → Document / - Image → Image / - Music → Musique / - Video → Vidéo	Medium
12.00	REG_PLF305_ECMS_012	1.00	REG_PLF305_ECMS_012	Check WCM Content Selector in Chrome	Step 1: Open WCM Content Selector window	Use Chrome to test this case. / - Go to Content Explorer / - Create a free layout web content / - In main content FCK Editor, click on icon WCM Content Selector. This selector windows will open. / - On that new windows, open General drives/Sites Management/acme/documents.	The icon Upload File now appears.	Medium	ECMS-2119 / CCP-872	Pop-up does not close.
	REG_PLF305_ECMS_012	1.00	REG_PLF305_ECMS_012	Check WCM Content Selector in Chrome	Step 2: Open Upload File pop-up	- Click Upload File / - Click Browse then click Upload / - Click on Save button	The File Upload pop-up closes. The uploaded file is listed in WCM Content Selector windows.	Medium
13.00	REG_PLF305_ECMS_013	1.00	REG_PLF305_ECMS_013	Check FCK Editor in Chrome	Step 1: Check Document view	Use Chrome to test this case. / - Go to Content Explorer, drive Sites Management / - Go to acme/web contents/site artifacts / - Click on the document 'ACME Footer'	In tab Document view, there is a line saying “eXo Powered by eXo Platform 3.0”. This line is centered.	Medium	ECMS-2137 / CCP-881	The line is not centered.
	REG_PLF305_ECMS_013	1.00	REG_PLF305_ECMS_013	Check FCK Editor in Chrome	Step 2: Check in edit form	- Click Edit document	In Main Content the line “eXo Powered by eXo Platform 3.0” is still centered.	Medium
14.00	REG_PLF305_ECMS_014	1.00	REG_PLF305_ECMS_014	Inject java script	Step 1: In public acme, inject java script	- Don't login. Go to ACME site's Contact Us page (the link of this page is “Question” in acme home page) / - Put <script>alert('java script executed')</script> into one of the textual input fields (for example field Your Name) / - Complete all required fields then click Send	Confirmation page is shown to alert that your comment has been received	High	ECMS-2174 / CCP-902
	REG_PLF305_ECMS_014	1.00	REG_PLF305_ECMS_014	Inject java script	Step 2: Open injected document as root	- Log in as root / - Go to ContentExplorer --> Sites Management --> acme --> documents / - There will be a newly document saved there. Double click to open it.	The javascript does not get executed. There is no message box 'java script executed' displays	High	ECMS-2174 / CCP-902	java script gets executed.
15.00	REG_PLF305_ECMS_015	1.00	REG_PLF305_ECMS_015	Check multi value flag in View Node Properties	Step 1: Open form to add property for node	- Go to Content Explorer / - Create a Content Folder “test” / - View Node Properties	Property Management pop-up is shown	High	ECMS-2175 / CCP-903
	REG_PLF305_ECMS_015	1.00	REG_PLF305_ECMS_015	Check multi value flag in View Node Properties	Step 2: Add property for node	- Click Add a new property tab / - Put name is multiValueProperty / - Select multipe: true / - Add 2 values are “AAA” and “BBB” / - Save	New property is listed in View Node Properties tab	High
	REG_PLF305_ECMS_015	1.00	REG_PLF305_ECMS_015	Check multi value flag in View Node Properties	Step 3: Remove one values	- Go to View Node Properties tab / - Click on Edit icon of new added propery / - Remove value "BBB" / - Save	Value BBB is removed	High
	REG_PLF305_ECMS_015	1.00	REG_PLF305_ECMS_015	Check multi value flag in View Node Properties	Step 4: Import and export	- Click 'Export Node' to export 'test' node. / - Click 'Import Node' to import the exported xml file under 'test' node.	You will find a new 'test' node under the first 'test' node	High
	REG_PLF305_ECMS_015	1.00	REG_PLF305_ECMS_015	Check multi value flag in View Node Properties	Step 5: Verify multi value flag	- View Node Properties of the imported node / - Check value of Multi Value flag of “multiValueProperty”	The flag is 'false'	High
16.00	REG_PLF305_ECMS_016	1.00	REG_PLF305_ECMS_016	Upload a pdf file with user-input name	Step 1: Upload a pdf file with not empty name	- Go to Content Explorer, open any folder / - Click upload button / - Choose pdf file / - Type a name, for example “test” / - Save / - Right click on Uploaded file and select Edit	The node name is “test”, the file name is original name	Medium	ECMS-2272 / CCP-951	The node name is original name
17.00	REG_PLF305_ECMS_017	1.00	REG_PLF305_ECMS_017	Manage Publications	Step 1: Create a document	- Go to Content Explorer / - Create an article, input required fields / - Click Save as draft (Don't click Close)	The document is created with lock status. (See in the tree )	High	ECMS-2337 / CCP-798 / CCP-807	Unknown error and exception.
	REG_PLF305_ECMS_017	1.00	REG_PLF305_ECMS_017	Manage Publications	Step 2: Manage Publications	- Click Manage Publications / - Under section Scheduled, click at “to” text box then select a date / - Click Save (don't input “from”, don't change Status)	No exception.	High

## Bugs_v2_1_6
	TEST CASES					Passed	0	0	0	0
				Failed	0	0	0	0
	Function List:	Bugs on ECMS 2.1.6 for regression test					Blocked	0	0	0	0
	Total Main Cases:	15					Untested	0	0	0	0
				N/A	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
1.00	REG_PLF306_ECMS_001	1.00	REG_PLF306_ECMS_001	Check limit of category length	Step 1: Open form to edit category tree	- Go to Content Administration → Categories&Tags / - Go to Manage Categories / - Click on Edit icon of 1 category tree	Edit Category Tree pop-up is shown. It allows to add categories inside	High	ECMS-1538 / CCP-621	System warning "The name too long"
	REG_PLF306_ECMS_001	1.00	REG_PLF306_ECMS_001	Check limit of category length	Step 2: Open form to add category	- Select the path to add category in the left pane. / - Click on Add icon	Form to add new category appears	High
	REG_PLF306_ECMS_001	1.00	REG_PLF306_ECMS_001	Check limit of category length	Step 3: Check the limit of category length	- In Category Name field, put the name of category is greater than 30 characters (and less than 150) / - Click Save button	Save successfully.	High
2.00	REG_PLF306_ECMS_002	1.00	REG_PLF306_ECMS_002	Check RTF Document Edition Dialog	Step 1: Open soffice	- Open terminal and run soffice / - Run command: / Soffice -headless -accept="socket,host=127.0.0.1,port=8100;urp;" -nofirststartwizard / - Restart server	Run successfully.	High	ECMS-1895 / CCP-734	Text area display in Edit dialog.
	REG_PLF306_ECMS_002	1.00	REG_PLF306_ECMS_002	Check RTF Document Edition Dialog	Step 2: Upload a rtf file	- Go to Content Explorer / - Select Site Management drive / - Select acme/documents / - Upload a RTF file / - View content of uploaded file	Content of uploaded file is shown	High
	REG_PLF306_ECMS_002	1.00	REG_PLF306_ECMS_002	Check RTF Document Edition Dialog	Step 3: Edit uploaded file	- Select this file and select Edit Document / - In Edit Document form, click on Trash icon to remove this document / - Upload a new RTF file / - Click Save and Close button / - View content of RTF file	After 10m (in ECMS), new content of uploaded file is shown.	High
3.00	REG_PLF306_ECMS_003	1.00	REG_PLF306_ECMS_003	Check server start-up with specified language	Step 1: Configure file	- On Linux, open file exoenv.sh and add this line: / - On Window, open file exoenv.bat and add this line: / JAVA_OPTS="$JAVA_OPTS -Duser.language=zh -Duser.region=CN" / - Save this file	File is save	High	ECMS-1952 / CCP-761	Exception in the console
	REG_PLF306_ECMS_003	1.00	REG_PLF306_ECMS_003	Check server start-up with specified language	Step 2: Start server	Start server	Server starts without error	High
4.00	REG_PLF306_ECMS_004	1.00	REG_PLF306_ECMS_004	Check permission removal on document	Step 1: Creates a document	- Login as John / - Go to Content Explorer / - Select drive Site Management → acme/web contents / - Add a web content document	Web content document is created under Web Content folder	Medium	ECMS-2314 / CCP-919	Exception on console
	REG_PLF306_ECMS_004	1.00	REG_PLF306_ECMS_004	Check permission removal on document	Step 2: Add category for document	- Click on Manage categories / - Add 1 category under acme tree for this web content	Added category is listed on Referenced tab	Medium
	REG_PLF306_ECMS_004	1.00	REG_PLF306_ECMS_004	Check permission removal on document	Step 3: Remove permission	- Click Manage Permission / - Remove permission “any” and “*:/web-contributors”	Permission is removed	Medium
	REG_PLF306_ECMS_004	1.00	REG_PLF306_ECMS_004	Check permission removal on document	Step 4: Mary accesses the category	- Login as mary / - Go to Content Explorer, drive acme / - Select the category at step 2 / - Check if there is exception	No exception. Mary does not see the document.	Medium
5.00	REG_PLF306_ECMS_005	1.00	REG_PLF306_ECMS_005	Edit metadata with multi-value	Step 1: Configure	- Go to issue https://jira.exoplatform.org/browse/ECMS-2332 - Download file: wcm-ext-nodetypes.xml and replace the files webapps/ecm-wcm-extension/WEB-INF/conf/wcm-extension/wcm/nodetypes-configuration.xml / - Download file: dialog1.gtmpl and replace / webapps/ecm-wcm-extension/WEB-INF/conf/wcm-artifacts/nodetype-templates/siteMetadata/dialogs/dialog1.gtmpl / - On Jboss, download these files and replace into /server/default/deploy/ecm-wcm-extension- ...ear//ecm-wcm-extension.war/WEB-INF/conf/... / - Start server	Files are replaced	High	ECMS-2332 / CCP-982	Exception on console
	REG_PLF306_ECMS_005	1.00	REG_PLF306_ECMS_005	Edit metadata with multi-value	Step 2: Upload file	- Go to Content Explorer / - Open form to upload a file / - Choose a file to upload / - Click Save. Still keep upload file form	File is choose to upload	High
	REG_PLF306_ECMS_005	1.00	REG_PLF306_ECMS_005	Edit metadata with multi-value	Step 3: Edit metadata	- Click on Edit icon in Manage Metadata columm / - Add metadata button / - Choose _metadata:siteMetadata and / - Click Add / - Select List External Metadata tab / - Click on edit icon of metadata:siteMetadata / - In metedate edit form, there will be a select box. Select some values then save.	Save successfully. No exception.	High		Cannot save.
6.00	REG_PLF306_ECMS_006	1.00	REG_PLF306_ECMS_006	Search and download file of which name contain apostrophe ( character ' )	Step 1: Upload file	- Prepare a file of which name contains apostrophe (character ' ) / - Go to Content Explorer, acme/documents to upload the file	File is uploaded successfully.	Medium	ECMS-2317 / CCP-978
	REG_PLF306_ECMS_006	1.00	REG_PLF306_ECMS_006	Search and download file of which name contain apostrophe ( character ' )	Step 2: Search the file	- Go to acme home page / - Search the file by its name	File link display correctly in search result	Medium		The apostrophe character displays as %27
	REG_PLF306_ECMS_006	1.00	REG_PLF306_ECMS_006	Search and download file of which name contain apostrophe ( character ' )	Step 3: Download file in search result	- Click to download the file	Download successfully	Medium		Cannot download
7.00	REG_PLF306_ECMS_007	1.00	REG_PLF306_ECMS_007	Check page navigation in File Explorer	Step 1: Import much content	- Download this file : https://jira.exoplatform.org/secure/attachment/36575/36575_sysview.xml / - Go to content explorer / - Import node using the downloaded file	File is imported successfully	Medium	ECMS-2363 / CCP_994	Page number navigation never displays
	REG_PLF306_ECMS_007	1.00	REG_PLF306_ECMS_007	Check page navigation in Content Explorer	Step 2: Edit Layout	- Go to Group Edit / - Edit Layout, remove the footer portlet / - Save Layout	Footer portlet is removed.	Medium
	REG_PLF306_ECMS_007	1.00	REG_PLF306_ECMS_007	Check page navigation in Content Explorer	Step 3: Edit Page	- Go to Group Edit / - Edit page, remove Authoring portlet / - In tab Edit Mode, uncheck “Show Filter Bar” / - Save / - Check display of the page	Page number navigation displays well	Medium
8.00	REG_PLF306_ECMS_008	1.00	REG_PLF306_ECMS_008	Check content sort order in CLV	Step 1: Edit Overview page	- Go to page acme/Overview / - Edit portlet configuration of the portlet “Latest news” / - Sort 'Descendant' by 'Modified date'	Content is sorted correctly by modified date	Medium	ECMS-2402 / CCP-1003	Overview page is OK but News page is not.
	REG_PLF306_ECMS_008	1.00	REG_PLF306_ECMS_008	Check content sort order in CLV	Step 2: Edit News page	- Go to page acme/News / - Edit portlet configuration of the portlet “News” / - Sort 'Descendant' by 'Modification date'	Content is sorted correctly by modified date	Medium
	REG_PLF306_ECMS_008	1.00	REG_PLF306_ECMS_008	Check content sort order in CLV	Step 3: Edit a content to make it the newest modified content	- Go to Content Explorer / - Edit a content in acme/categories/acme	Content is edited	Medium
	REG_PLF306_ECMS_008	1.00	REG_PLF306_ECMS_008	Check content sort order in CLV	Step 4: Check sort order in Overview page	- Go to Overview page and check if the content is sorted correctly	Content is sorted correctly	Medium
	REG_PLF306_ECMS_008	1.00	REG_PLF306_ECMS_008	Check content sort order in CLV	Step 5: Check sort order in News page	- Go to News page and check if the content is sorted correctly	Content is sorted correctly	Medium
9.00	REG_PLF306_ECMS_009	1.00	REG_PLF306_ECMS_009	Check Portuguese translation	Step 1: Portuguese translation	- Select language Portuguese / - Go to Site Administration / - Go to Manage Views / - Edit a view to check the translation of Edit form	Portuguese translation is well-done. / Save → Salva / Cancel → Cancelar	High	ECMS-2448 / CCP-1014	Cancelar → Cancelarl. / And there is a backslash in Salva and Cancelar button
10.00	REG_PLF306_ECMS_010	1.00	REG_PLF306_ECMS_010	Check Edit form of a File document	Step 1: Add a document	- Go to Content Explorer / - Create a document / - Select template 'File' / - Input name and content / - Save and Close	File document is created successfully	High	ECMS-2478 / CCP-1023	Right after selecting new category, field WYSIWYG is reset.
	REG_PLF306_ECMS_010	1.00	REG_PLF306_ECMS_010	Check Edit form of a File document	Step 2: Edit a document	- Edit document above / - Change the WYSIWYG field value / - Select a new category / - Save	Changes are saved	High
11.00	REG_PLF306_ECMS_011	1.00	REG_PLF306_ECMS_011	Check link in WYSIWYG field	Step 1: Check link in WYSIWYG field	- Go to siteExplorer. / - Create a new article. / - Switch the WYSIWYG to source mode / - Paste in the source : <a href="www.google.com">performance on red</a> / - Switch out of source mode / - Save as draft	The link displays well	High	ECMS-2504 / CCP-1029	Links that contains the word “on” are corrupted
12.00	REG_PLF306_ECMS_012	1.00	REG_PLF306_ECMS_012	Check 'Add Translation' with Simplified Chinese	Step 1: Add zh language to article dialog	- Go to Content Administration, Manage Templates / - Edit template exo:article / - In tab Dialog, select to edit the existing dialog / - Find a line like this : / String[] fieldLang = ["jcrPath=/node/exo:language", "options=en,fr,es,de", lang] ; / - Add 'zh' to it: / String[] fieldLang = ["jcrPath=/node/exo:language", "options=en,fr,es,de,zh", lang] ; / - Save this file	Dialog of Article template is edited successfully	High	ECMS-2596 / CCP-1052	en content displays
	REG_PLF306_ECMS_012	1.00	REG_PLF306_ECMS_012	Check 'Add Translation' with Simplified Chinese	Step 2: Add documents	- Go to Content Explorer / - Add an article with lang=en, save / - Add another article with lang=zh, save / - Publish 2 documents above	- 2 documents are created & published	High
	REG_PLF306_ECMS_012	1.00	REG_PLF306_ECMS_012	Check 'Add Translation' with Simplified Chinese	Step 3: Add translation for en-article	- Select en-article / - Open form to add translation / - Select zh-article to be translation of en-article	- zh article is added add translation of en article	High
	REG_PLF306_ECMS_012	1.00	REG_PLF306_ECMS_012	Check 'Add Translation' with Simplified Chinese	Step 4: Add a page to display the document	- Create a new page add Content Detail portlet into this page / - Select en-article as content of this page / - Save the page	The en content displays	High
	REG_PLF306_ECMS_012	1.00	REG_PLF306_ECMS_012	Check 'Add Translation' with Simplified Chinese	Step 5: Check the displaying of zh-article	- Change the language to Simplified Chinese	The zh content displays	High
13.00	REG_PLF306_ECMS_013	1.00	REG_PLF306_ECMS_013	Check Space Document	Step 1: Create and invite user as member of space	- Login as demo, create a space / - Click on Space Setting icon / - Select Member tab / - Invite Mary to join this space	New space is created successfully	High	ECMS-2660 / CCP-1032	Private drive opens
	REG_PLF306_ECMS_013	1.00	REG_PLF306_ECMS_013	Check Space Document	Step 2: Check Space Setting icon	- Login as mary / - Go to Public space / - Accept invitation / - Go to this space / - Click on Documents tab	Drive of space is shown	High
14.00	REG_PLF306_ECMS_013	2.00	REG_PLF306_ECMS_013	Check Group drives	Step 1: Check group drives	- Login as john / - Go to Content Explorer / - Check how many group drives John see	The number of drive depend on the number of group that John join in	High	ECMS-2697 / CCP-1032	John does not see new drive, even after logout/re-login
	REG_PLF306_ECMS_013	2.00	REG_PLF306_ECMS_013	Check Group drives	Step 2: Add a new membership for john	- Go to User and Group Management / - Add john to a new group (or a group with new membership as well)	John is added into new group	High
	REG_PLF306_ECMS_013	2.00	REG_PLF306_ECMS_013	Check Group drives	Step 3: Re-check group drives	- Go to Content Explorer and check if john can see a new group drive	There is a new group drive	High
15.00	REG_PLF306_ECMS_014	1.00	REG_PLF306_ECMS_014	Check Manage Publication Panel template	Step 1: Check Manage Publication form	- Login as john / - Go to Content Explorer, Site Management drive / - Open node acme/web content/site artifacts/contact_form_confirmation (or any node that has never had a publication status) / - Click Manage Publication / - Select States and versions based publication	No exception.	High	ECMS-2699 / CCP-1104	Exception in console

## Bugs_v2_1_7
	TEST CASES					Passed	0	0	0	0
				Failed	0	0	0	0
	Function List:	Bugs on ECMS 2.1.7 for regression test					Blocked	0	0	0	0
	Total Main Cases:	20					Untested	0	0	0	0
				N/A	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
1.00	REG_PLF307_ECMS_001	1.00	REG_PLF307_ECMS_001	"View Properties" Component	Step 1: Create an article with HTML content containing <table> tags into the source view of the WYSIWYG of summary field.	- Go to Site Explorer and select article template / - Create an article, in summary field, click source and paste the HTML content in file below / https://jira.exoplatform.org/secure/attachment/39483/html.txt / - Save the content	Article is created	High	ECMS-2526 / CCP-1033
	REG_PLF307_ECMS_001	1.00	REG_PLF307_ECMS_001	"View Properties" Component	Step 2: View Node Properties of article	- Click on "View Node Properties" / - Refresh the browser window	- The dialog of the component is shown. / - There is no broken UI on "View Node Properties" dialog	High	ECMS-2526 / CCP-1033	- Click on "View Node Properties" and you will find that the dialog of the component is not shown. / - If you refresh the browser window then you will see the dialog with broken UI.
2.00	REG_PLF307_ECMS_002	1.00	REG_PLF307_ECMS_002	Replacing a file in categories	Step 1: Upload a file	- Go to File Explorer / - Create 1 folder / - Select 1 file to upload	File is uploaded	High	ECMS-2321 / CCP-880
	REG_PLF307_ECMS_002	1.00	REG_PLF307_ECMS_002	Replacing a file in categories	Step 2: Upload the same file twice	- Select created folder above / - Upload the same file again. / - Choose "Replace data".	The existed file is replaced	High		An error message appears "The name "name of upload field" is existing. You can not upload same name file except for 'nt:file'".
3.00	REG_PLF307_ECMS_003	1.00	REG_PLF307_ECMS_003	Selecting the 'workflow' publication workflow	Step 1: Config to run workflow	- Before starting server, copy file ecmworkflow-extension.xml in / https://jira.exoplatform.org/secure/attachment/38705/ecmworkflow-extension.xml + In PLF Tomcat: / 1. paste in folder tomcat/conf/Catalina/localhost / 2. run ./start_eXo.sh all / + in PLF JBOSS: / 1. Paste in server/default/deploy / 2. Go to bin folder, edit run.conf as line below: / # Platform environment variables / EXO_PROFILES="-Dexo.profiles=default,workflow" / 2.1 On Window: go to bin folder, edit run,conf.bat as line above / - Start server normally	Server starts successfully without exception	High	CCP-1066 ECMS-2335
	REG_PLF307_ECMS_003	1.00	REG_PLF307_ECMS_003	Selecting the 'workflow' publication workflow	Step 2: Click Manage publications at node with no publication status	- Login as john / - Go to Content Explorer / - Open this node: /acme/web contents/site artifacts/contact_form_confirmation or any node with no publication status / - Click Manage publications and select the first option: workflow / - Click Save	There is no exception	High	CCP-1066 ECMS-2335	Throw out exception
4.00	REG_PLF307_ECMS_004	1.00	REG_PLF307_ECMS_004	Images in ACME Site	Step 1: Edit one document under acme logo and republish it	- Login then go to http://localhost:8080/ecmdemo/private/acme / - Change to Edit mode / - Edit one document which is found under acme logo → Save as draft → Republish it.	Document is edited & published	High	CCP-1005 ECMS-2426
	REG_PLF307_ECMS_004	1.00	REG_PLF307_ECMS_004	Images in ACME Site	Step 2: Refresh browser	- Return http://localhost:8080/ecmdemo/private/acme then refresh this page	Illustration of republished document is displayed well, even users refresh many times	High		illustration of document is visible then disappears and reappears after refreshing pages
5.00	REG_PLF307_ECMS_004	2.00	REG_PLF307_ECMS_004	Images in ACME Site	Step 1: Create a Free Web Content document with illustration and add it into a CLV page	- Login / - Go to Content Explorer and create 2 free layout web contents with illustration which the second one is inside the first one then publish them / - Create new page then add Content List Portlet. Choose directory containing these new web content	Illustration of this document is displayed well, even users refresh many times	High	CCP-1005 ECMS-2426	illustration of document is visible then disappears and reappears after refreshing pages	N/A this case
6.00	REG_PLF307_ECMS_005	1.00	REG_PLF307_ECMS_005	*, ~, +, - characters in simple search and advanced search	Step 1: Create some documents with titles or content contain +, - characters, and some other documents	- Login / - Go to Content Explorer, choose a drive and create Create some documents with titles or content contain +, - characters, and some normal documents	Documents are created successfully	High	CCP-1019 ECMS-2452		Won't fix in wcm 2.1.x
	REG_PLF307_ECMS_005	1.00	REG_PLF307_ECMS_005	*, ~, +, - characters in simple search and advanced search	Step 2: Search with * and ~ character in Simple search,	- Fill in simple search box above action bar * character, Click Search or press Enter / - Fill in simple search box above action bar part of document then ~ character, Eg: condi~, Fir~. Click Search or press Enter	- All documents are listed in search result / - Return documents which contain these word in search result, eg: conditions.doc, Fire	High	CCP-1019 ECMS-2452	- Cannot search with * / - Cannot search with "~"
	REG_PLF307_ECMS_005	1.00	REG_PLF307_ECMS_005	*, ~, +, - characters in simple search and advanced search	Step 3: Search with + and – character in advanced search	- Click Saved search then Advanced search / - Fill in search by name tab title of document with + or – characters	All document with title or content containing these characters are listed in search result and no exception	High	CCP-1019 ECMS-2452	- raise exception
7.00	REG_PLF307_ECMS_006	1.00	REG_PLF307_ECMS_006	Linked documents of article is click-able in a SCV page	Step 1: Create an article	- Log into the ecmdemo portal. / - Go to Content Explorer. / - Create a new article. / - Save &close	Article is created	High	CCP-1031 ECMS-2511
	REG_PLF307_ECMS_006	1.00	REG_PLF307_ECMS_006	Linked documents of article is click-able in a SCV page	Step 2: Add a related link for article	- Select Article above / - Click on Manage Relation on action bar (Pls add this action into the view that you're using if you don't see it) / - Select 1 document to be relation of Article document	Article is linked to a document	High	CCP-1031 ECMS-2511
	REG_PLF307_ECMS_006	1.00	REG_PLF307_ECMS_006	Linked documents of article is click-able in a SCV page	Step 3: Publish article	- Select Article and published / - Select document is relation of Article and publish	Both Article and this relation are published	High	CCP-1031 ECMS-2511
	REG_PLF307_ECMS_006	1.00	REG_PLF307_ECMS_006	Linked documents of article is click-able in a SCV page	Step 4: Add Article in a SCV	- Create a page with Content detail portlet and choose article above as content	SCV is displayed with the content of article and a link beneath	High	CCP-1031 ECMS-2511
	REG_PLF307_ECMS_006	1.00	REG_PLF307_ECMS_006	Linked documents of article is click-able in a SCV page	Step 5: Click on the link of article	- Click on the link	Show detail of the linked document	High	CCP-1031 ECMS-2511	The related links are not clickable : code source displayed and if there is no related documents, label link is still displayed
8.00	REG_PLF307_ECMS_007	1.00	REG_PLF307_ECMS_007	Check the displaying of Content based on custom node type a CLV page	Step 1: Create a new name space	- Login as root / - Go to Content Administration/ Content Types/ Namespace Registry: Create a new namespace with Namespace Prefix is "zzz"	A new namspace is created	High	CCP-1082 ECMS-2687
	REG_PLF307_ECMS_007	1.00	REG_PLF307_ECMS_007	Check the displaying of Content based on custom node type a CLV page	Step 2: Create a new node type	- Go to Content Types -> Manage Node type / - Add a new node type / * Choose Name Space: zzz / * node type name: nodetype1 / * super type: nt:base / * Move to tab Property: choose name space zzz, definition name: titulo, Click Add Property / * click on save on Node type tab	A new node type is created	High	CCP-1082 ECMS-2687
	REG_PLF307_ECMS_007	1.00	REG_PLF307_ECMS_007	Check the displaying of Content based on custom node type a CLV page	Step 3: Create a new template	- Click on Content Presentation -> Manage Templates / - Add the new template with label "Teste do nodetype1" / - Choose "Any permission" and save it.	A new template is created	High	CCP-1082 ECMS-2687
	REG_PLF307_ECMS_007	1.00	REG_PLF307_ECMS_007	Check the displaying of Content based on custom node type a CLV page	Step 4: Create content folder in classic/ web contents	Click on the "Content Explorer" tab > Create a new content folder "test_nodetype" in "/classic/web contents	Content folder is created	High	CCP-1082 ECMS-2687
	REG_PLF307_ECMS_007	1.00	REG_PLF307_ECMS_007	Check the displaying of Content based on custom node type a CLV page	Step 5: Create 2 contents and publish them	- Click on "Add Content" / - Choose the template "Teste do nodetype1" / - You can write anything in the fields, don't fill up the jcr_mixinTypes / - Click on "Save as draft" / - Click on close / - Click on manage publications -> published	2 Documents are created and published	High	CCP-1082 ECMS-2687
	REG_PLF307_ECMS_007	1.00	REG_PLF307_ECMS_007	Check the displaying of Content based on custom node type a CLV page	Step 6: Add a CLV in classic overview page	- Go to Classic/ overview page / - Click on "Site Editor -> Edit Page" / - Add a "Content List" portlet / - Edit the "content list" to set the "Folder Path" to the /classic/web contents/test_nodetype folder / - Click on Save / - Click on Close / - Click on the Finish button	The two contents are shown in the "content list" in over page	High	CCP-1082 ECMS-2687	It will show the Overview page again. The two contents should be showed in the "content list", but we see the "Sorry, no articles available" message
9.00	REG_PLF307_ECMS_008	1.00	REG_PLF307_ECMS_008	Check right URL when in put title of node with specical characters in IE 7 and IE 8	Step 1: In edit mode, Create 2 articles with name containing special characters	- Log in as root / - In Edit mode in acme/overview, use the icon on the list viewer portlet to Add Content / - Create 2 articles with titles 'Rakı','végétarisme' (Note that the name will be set to rakı as a result of the LocalizationConnector sanitation) / - Go back to the home page and open the new articles.	The right content is shown in the detail portlet.	High	CCP-1098 ECMS-2720	A wrong content is shown in the detail portlet (show ACM introduce page)
10.00	REG_PLF307_ECMS_009	1.00	REG_PLF307_ECMS_009	Check search result with keyword in comment of document	Step 1: Create document	- Go to the drive acme-category in the Sites Explorer / - Select any category / - Create 1 document in this category	Document is created successfully	High	CCP-1121 ECMS-2787	An error appears
	REG_PLF307_ECMS_009	1.00	REG_PLF307_ECMS_009	Check search result with keyword in comment of document	Step 2: Comment for document	- Select created document above / - Select Collaboration tab / - Add 1 comment for document	Comment is added	High
	REG_PLF307_ECMS_009	1.00	REG_PLF307_ECMS_009	Check search result with keyword in comment of document	Step 3: Check the displaying of node 1	- Back to the root and do a search with any word which is found in the comment	Search result contains the node having the relevant comment	High
11.00	REG_PLF307_ECMS_010	1.00	REG_PLF307_ECMS_010	Check the displaying of Content explorer portlet in 'level3' page	Step 1: Create new page	- Login acme site as root. / - Create new page named "level1"	Page is created	High	CCP-1134 ECMS-2902	The portlet contents / content explorer is corrupted
	REG_PLF307_ECMS_010	1.00	REG_PLF307_ECMS_010	Check the displaying of Content explorer portlet in 'level3' page	Step 2: Create child page of page1	- Select page “level1” / - Add new page "level2" children of "level1"	Page is created	High
	REG_PLF307_ECMS_010	1.00	REG_PLF307_ECMS_010	Check the displaying of Content explorer portlet in 'level3' page	Step 3: Create a page at level 3 with content explorer portlet	- Add new page "level3" children of "level2" / - Drag the "content explorer" portlet into the new page "level3" / - Save.	The content explorer in "level3" page is showed	High
12.00	REG_PLF307_ECMS_011	1.00	REG_PLF307_ECMS_011	Check that Double left click on a node works properly in Chrome	Step 1: Left mouse double-click on a node	- Go to Sites Management / - Left mouse double-click on a node	Node is opened Mediumly	Medium	CCP-871 ECMS-2118	The dialog to ask for movement of this node appears.
13.00	REG_PLF307_ECMS_012	1.00	REG_PLF307_ECMS_012	Check delete Favorites folder in Private Drive of user	Step 1: Delete favorite folder in Private drive	- Login as root or john / - Go to Content Explorer / - Delete Favorite folder in the Private Driver	There is no exception	Medium	CCP-1056 ECMS-2617	Exception appears “javax.jcr.PathNotFoundException: Node not found /Users/root/Private/Favorites”
	REG_PLF307_ECMS_012	1.00	REG_PLF307_ECMS_012	Check delete Favorites folder in Private Drive of user	Step 2: Choose another drive/ folder	Choose another drive/ folder	No UI error and no exception	Medium	CCP-1056 ECMS-2617	UI error and Exception on console occur
14.00	REG_PLF307_ECMS_013	1.00	REG_PLF307_ECMS_013	Check "Add/Manage Content" actions from CLV in "Dynamic Navigation" active mode	Step 1: Check display of back button	- Start a clean server / - Log in and go to $POTAL/ecmdemo/private/acme/news then go to category / - Activate Edit mode / - Click on Add new content icon	Back button appears for user to click to come back to category	Medium	CCP-1045 ECMS-2580	Cannot find back button. Back button appears only we try to edit an available content in dynamic mode
	REG_PLF307_ECMS_013	1.00	REG_PLF307_ECMS_013	Check "Add/Manage Content" actions from CLV in "Dynamic Navigation" active mode	Step 2: Check location of new content	- Choose 1 template document / - Fill data in required fields / - Save / - Click Back button	New content is created in selected category	Medium	CCP-1045 ECMS-2580	Error on place of new created document. It's always created in /acme
15.00	REG_PLF307_ECMS_014	1.00	REG_PLF307_ECMS_014	Check load icon in Simple View	Step 1: Check load icon in Simple View	- Go to Group > Content Explorer / - Choose "/organization/management/executive-board drive / - Select Icon-view / - Click "Content Explorer" several time or refresh web browser.	Icon can be loaded and no error in Firebug	Medium	CCP-1109 ECMS-2455	Icons can not be loaded and get this error in Firebug : / * eXo.ecm.UISimpleView is undefined / * eXo.ecm.UISimpleView.errorCallback(this);
16.00	REG_PLF307_ECMS_015	1.00	REG_PLF307_ECMS_015	Check java.util.MissingResourceException when try to open a PDF file.	Step 1: Check java.util.MissingResourceException when try to open a PDF file.	- Change the portal language to Italian. / - Open the Content explorer / - Go to /acme/documents/ and open the metro.pdf file	pdf file is opened and there is no exception	Medium	CCP-1129 / ECMS-2836	We get the following exception "java.util.MissingResourceException: Can't find resource for bundle java.util.PropertyResourceBundle, key PDFViewer.label.nextPage".
17.00	REG_PLF307_ECMS_016	1.00	REG_PLF307_ECMS_016	Check: delete a node of a workspace different from trash one's	Step 1: Create document in dms-system workspace	- Go to Content Explorer > DMS Administration Drive / - Select any path and create 1 new content	New content is created	Medium	CCP-1127 ECMS-2826	error on console and Status Invalid on browser
	REG_PLF307_ECMS_016	1.00	REG_PLF307_ECMS_016	Check: delete a node of a workspace different from trash one's	Step 2: Add a related link for article	- Right click on create content above and select Delete	Document is remove successfully, no error in console	Medium
18.00	REG_PLF307_ECMS_017	1.00	REG_PLF307_ECMS_017	Check: Shared css and js is reloaded after server restart	Step 1: Create Css file	- Go to Content Explorer / - Select Sites Management drive / - Select /shared/css folder / - Create 1 css file with content: #ACMESignin {background-color:white;}	Css file is created	Medium	CCP-1100 ECMS-2763	The background is now grey, the global css is not taken effect.
	REG_PLF307_ECMS_017	1.00	REG_PLF307_ECMS_017	Check: Shared css and js is reloaded after server restart	Step 2: Restart server and check the effect of css file	- Stop the server and restart it / - Go to acme homepage, refresh and see that background of Signin portlet is white.	The background is now still white, the global css is taken effect	Medium
19.00	REG_PLF307_ECMS_018	1.00	REG_PLF307_ECMS_018	A node that don't point to a page does not have a link on Navigation portlet	Step 1: Create a node without page on ACME navigation	- Edit navigation of ACME site / - Add a navigation node (test 1) without adding a page to it.	Node test 1 is created successfully	Medium	CCP-1110 ECMS-2748	A page is displayed with the following message: "Page not found."
	REG_PLF307_ECMS_018	1.00	REG_PLF307_ECMS_018	A node that don't point to a page does not have a link on Navigation portlet	Step 2: Create child-node of step 1	- Select node 1 / - Add new node (test 2) is child node of test 1 / - Add a page for node test 2	Node test 2 (have a page) is created as child node of test 1	Medium
	REG_PLF307_ECMS_018	1.00	REG_PLF307_ECMS_018	A node that don't point to a page does not have a link on Navigation portlet	Step 3: Check the displaying of node 1	- Return to the home page and click on the first node created (test 1)	Web browser retains the current page.	Medium
20.00	REG_PLF307_ECMS_019	1.00	REG_PLF307_ECMS_019	Setting a content Explorer with parameterize option	Step 1: Setting a content Explorer with parameterize option	- Create a new page containing a site explorer portlet / - In the site explorer options / + choose Select Type as "Parameterize" / + Choose a drive. / + Select a path / - Save then close / - Save this page / - Open this page	File explorer point to the selected path	Medium	CCP-1035 ECMS-2717	File explorer doesn't point to the selected path

## Bugs_v2_1_8
	TEST CASES					Passed	0	0	0	0
				Failed	0	0	0	0
	Function List:	Bugs on ECMS 2.1.8 for regression test					Blocked	0	0	0	0
	Total Main Cases:	15					Untested	0	0	0	0
				N/A	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
1.00	REG_PLF308_ECMS_001	1.00	REG_PLF308_ECMS_001	Check whether unknown error appears when do action on document while trying to edit	Step 1: Create new document	- Login as root / - Go to Sites Explorer/Sites Management/acme/documents / - Add new document	New document is created successfully	High	CCP-1102 ECMS-2095
	REG_PLF308_ECMS_001	1.00	REG_PLF308_ECMS_001	Check whether unknown error appears when do action on document while trying to edit	Step 2: Add a SCV page	- Go to acme home page add a new SCV page / - Browse added document to be content of SCV, then save	SCV is created with added document successfully	High	CCP-1102 ECMS-2095
	REG_PLF308_ECMS_001	1.00	REG_PLF308_ECMS_001	Check whether unknown error appears when do action on document while trying to edit	Step 3: Change to Edit mode	- Select SCV page / - Change to edit mode / - Click edit icon to edit the document (inside SCV)	Document is opened in edit mode	High	CCP-1102 ECMS-2095
	REG_PLF308_ECMS_001	1.00	REG_PLF308_ECMS_001	Check whether unknown error appears when do action on document while trying to edit	Step 4: Click Request Approval or Publish	Click Request Approval or Publish	Document is sent to request approval or published, and can be view in Published mode in SCV and no exception	High	CCP-1102 ECMS-2095	Unknown error / Exception: / 16:24:17,770 ERROR [portal:UIPortalApplication] Error during the processAction phase / javax.jcr.lock.LockException: Node /sites content/live/acme/documents/testest is locked
2.00	REG_PLF308_ECMS_002	1.00	REG_PLF308_ECMS_002	Create and delete javascript files from Content Explorer	Step 1: Add JS document	- Log in / - Go to Site explorer/ Sites management / - Go to folder /acme/js / - Add JS document Test.js with content “alert("here is Acme site");”	New JS document is created successfully	High	CCP-961 ECMS-2297
	REG_PLF308_ECMS_002	1.00	REG_PLF308_ECMS_002	Create and delete javascript files from Content Explorer	Step 2: Check show javascript alert	- Go to acme homepage / - Clear cache and refresh	One alert is showed on ACME site “here is Acme site”	High	CCP-961 ECMS-2297	Go to Front-page site ACME the adding script is not loaded, even cache is cleared
	REG_PLF308_ECMS_002	1.00	REG_PLF308_ECMS_002	Create and delete javascript files from Content Explorer	Step 3: Delete JS file from acme/js folder	- Go to Site explorer/ Sites management / - Go to folder /acme/js / - Delete file Test.js above / - Clear cache and refresh browser	Alert does not appear again	High	CCP-961 ECMS-2297	Alert still appears though browser cache is cleared.
3.00	REG_PLF308_ECMS_003	1.00	REG_PLF308_ECMS_003	Check name is automatically generated when creating a new content	Step 1: Create new document which have title and name	- Go to Content Explorer and choose a drive / - Click Add Content on action bar / - Choose a template which has title and name, eg: Article, Free layout web content, Event, Sample node / - Fill name only	Title of document is automatically generated, and no JS error is shown	High	ECMS-2441	Name is not automatically generated and JS error is shown : eXo.ecm.SELocalization is undefined
4.00	REG_PLF308_ECMS_004	1.00	REG_PLF308_ECMS_004	Check whether Uploaded image gets overwritten	Step 1: Upload an image	- Login and go to content explorer, choose a drive / - Upload an image / - Open this image to preview	Image is uploaded successfully and well previewed	High	CCP-1152 ECMS-3059		N/A this case
	REG_PLF308_ECMS_004	1.00	REG_PLF308_ECMS_004	Check whether Uploaded image gets overwritten	Step 2: Upload another image which has the same extension	- Click Upload file on action bar and upload file successfully	Name and content of the first uploaded image is previewed, you can view the second image is child of the first image by ticking Enable DMS Structure in advanced option of Set up your browsing preferences	High	CCP-1152 ECMS-3059	The first image that was in the preview gets replaced by the second uploaded image keeping the same title but without any warning.
5.00	REG_PLF308_ECMS_005	1.00	REG_PLF308_ECMS_005	Check Search results are displayed 10 items per page	Step 1: Create many document	- Go to Content explorer, choose a drive / - Create a document containing a key word (Eg, search) / - Copy and paste this document more than 100 times	More than 100 document is created	High	ECMS-3104 / CCP-1166
	REG_PLF308_ECMS_005	1.00	REG_PLF308_ECMS_005	Check Search results are displayed 10 items per page	Step 2: Set up node displayed per page	- Click Set up your browsing preferences / - Setting 'Nodes Per Page' is 10	10 nodes will be displayed per page	High	ECMS-3104 / CCP-1166
	REG_PLF308_ECMS_005	1.00	REG_PLF308_ECMS_005	Check Search results are displayed 10 items per page	Step 3: Do Search	Fill 'search' in simple search box above action bar	There is more than 100 results of search divided in many pages. Each page should show 10 items per page	High	ECMS-3104 / CCP-1166	Search result does not display 10 nodes per page
6.00	REG_PLF308_ECMS_006	1.00	REG_PLF308_ECMS_006	Check displaying of Content Explorer portlet in home page	Step 1: Add Content Explorer portlet into homepage	- Login as root / - Go to acme home page / - Edit page then add Content Explorer portlet	Home page is displayed with Content explorer portlet	High	CCP-1185 ECMS-3249
	REG_PLF308_ECMS_006	1.00	REG_PLF308_ECMS_006	Check displaying oof Content Explorer portlet in home page	Step 2: Click acme drive in Content explorer portlet	Click acme drive in Content explorer portlet	Content of acme drive is shown inside portlet and no error	High	CCP-1185 ECMS-3249	Back to homepage then click acme driver on CE portlet -> error
7.00	REG_PLF308_ECMS_007	1.00	REG_PLF308_ECMS_007	Click on "View document" in a space	Step 1: Create a new space	- Login / - Go to intranet and add a new space / - Choose Documents tab	New space is created and document tab is choosen	High	ECMS-3302
	REG_PLF308_ECMS_007	1.00	REG_PLF308_ECMS_007	Click on "View document" in a space	Step 2: Upload a document and View it	- Upload a document / - Right click it and choose "View document"	Content of document is displayed well	High	ECMS-3302	You'll be redirected to the space's home page instead of viewing the document
8.00	REG_PLF308_ECMS_008	1.00	REG_PLF308_ECMS_008	Check applying two filters in the Filter By Type of File Explorer	Step 1: Create some documents and upload files	- Login / - Access to Site Explorer / - Add some documents and images in a drive (Eg: Collaboration)	Document is created/ files is uploaded	High	CCP-1196 ECMS-3316
	REG_PLF308_ECMS_008	1.00	REG_PLF308_ECMS_008	Check applying two filters in the Filter By Type of File Explorer	Step 2: Choose filters: Document and Image	- In the filter by type of the sidebar, choose two filters: Document and Image	Documents and image is shown as filler	High	CCP-1196 ECMS-3316	Nothing is shown in the drive. The filter Contents is not working too
9.00	REG_PLF308_ECMS_009	1.00	REG_PLF308_ECMS_009	Check the results of an initial research is cleared during a second search	Step 1: Create 5 or more documents with 'auto' word	- Go to Content explorer, create 5 or more documents with 'auto' word	Document is created	High	ECM-5584 / CCP-1210
	REG_PLF308_ECMS_009	1.00	REG_PLF308_ECMS_009	Check the results of an initial research is cleared during a second search	Step 2: Create more than 100 documents with 'colpin' word	- Create 100 documents with 'colpin' word	Document is created	High	ECM-5584 / CCP-1210
	REG_PLF308_ECMS_009	1.00	REG_PLF308_ECMS_009	Check the results of an initial research is cleared during a second search	Step 3: Search with word “auto”	- Fill in the simple search above action bar the word “auto”	- All documents with word 'auto' is displayed	High	ECM-5584 / CCP-1210
	REG_PLF308_ECMS_009	1.00	REG_PLF308_ECMS_009	Check the results of an initial research is cleared during a second search	Step 4: Search with word “colpin”	- Fill in the simple search above action bar the word “colpin”	Search result of above search is cleared and Display new search result with all documents with "colpin" word	High	ECM-5584 / CCP-1210	The second query contains more than 100 documents, the results of the second search will be added to the first
10.00	REG_PLF308_ECMS_010	1.00	REG_PLF308_ECMS_010	Searching under a category in Sites Explorer	Step 1: Search with Saved search	- Login / - Go to Content Explorer > Site management / - Click Saved Search then choose Created Document	All created documents are listed	Medium	CCP-970 ECMS-2309	* Error 1: Duplicated results on the 1st and 2nd page. / * Error 2: Wrong in number of displayed results.
11.00	REG_PLF308_ECMS_010	2.00	REG_PLF308_ECMS_010	Searching under a category in Sites Explorer	Step 1: Search under category	- Login / - Go to Site Explorer > Site Management >acme > categories > acme / - Search with keyword 'Power' in simple search box	Documents are included in the search results with each document is in different path / Title of document is displayed not name.	Medium	CCP-970 ECMS-2309	* Lack of 1 symlink for New1 on result. / * Titles should be displayed instead of name
12.00	REG_PLF308_ECMS_010	3.00	REG_PLF308_ECMS_010	Searching under a category in Sites Explorer	Step 1: Do a search which provides more than 100 results	- Create more than 100 documents / - Do search with a keyword in these documents	The result of previous search is clean, and display search result of these document	Medium	CCP-970 ECMS-2309	The result of previous search isn't clean.
13.00	REG_PLF308_ECMS_011	1.00	REG_PLF308_ECMS_011	Check nullPointerException when Setting a name to taxonomyAction	Step 1: Add Taxonomy Tree	- Go to 'Administration'/ 'Manage Categories', Click 'Add Taxonomy Tree' / - Set Name to 'test' and fill other fields and its permission / - Proceed to 'Add an action to the taxonomy tree' / - Click 'Save' and 'Next'	The Taxonomy Tree is created successfully	Medium	CCP-1150 ECMS-3057
	REG_PLF308_ECMS_011	1.00	REG_PLF308_ECMS_011	Check nullPointerException when Setting a name to taxonomyAction	Step 2: Create new node type in Form builder	- Go to 'Form Builder' / - Fill 'Name' and 'Description' / - Click 'Save'	New node type is created successfully, and no exception	Medium	CCP-1150 ECMS-3057	You will see NullPointerException.
14.00	REG_PLF308_ECMS_012	1.00	REG_PLF308_ECMS_012	Check displaying HTM Lists in exo content.	Step 1: Create free Layout webcontent	- Go to Site Explorer and select free Layout webcontent. / - Create new content and paste this HTML content into the source view of the WYSIWYG of summary field. / <ul> / <li>AAAAA</li> / <li>BBBBB</li> / <li>CCCCC</li> / <li>DDDDD</li> / <li>EEEEE</li> / <li>FFFFF</li> / </ul> / - Save the content	Content of free layout web content is displayed as a list	Medium	ECMS-3131 / CCP-1167	the HTML list was not displayed
15.00	REG_PLF308_ECMS_013	1.00	REG_PLF308_ECMS_013	Check Hidden Field's value is reset when editing a document	Step 1: Create a new node type "exo:mynodetype	- Login / - Go to Content Administration/ / Content Types/ Manage Node Type / - Create a new node type with / + namespace: exo / + node name: mynodetype / + super type: nt:base" / Select Property tab with / + namespace: exo / + Put Definition Name: content	exo:mynodetype is created successfully	Medium	CCP-1177 ECMS-3227
	REG_PLF308_ECMS_013	1.00	REG_PLF308_ECMS_013	Check Hidden Field's value is reset when editing a document	Step 2: Create new template named mynodetype	- Go to Content Administration/ / Content Presentation/ Manage Templates / - Click Add / - Choose name: exo: mynodetype, / Label: mynodetype / Set permission / - In dialog tab, paste content as file: https://jira.exoplatform.org/secure/attachment/49397/49397_dialog.gtmpl / - Click Save	New template is created successfully	Medium	CCP-1177 ECMS-3227
	REG_PLF308_ECMS_013	1.00	REG_PLF308_ECMS_013	Check Hidden Field's value is reset when editing a document	Step 3: Create new node with new template in CE and view node properties	- Go to CE / - Add Content, choose template mynodetype above and fill in 2 boxes with "content of my node", Click Save / - Click View Node Properties on action bar	- New node is created successfully / - There will be a property exo_content with value is content of my node	Medium	CCP-1177 ECMS-3227
	REG_PLF308_ECMS_013	1.00	REG_PLF308_ECMS_013	Check Hidden Field's value is reset when editing a document	Step 4: Edit dialog content	Go back to site administration, edit dialog of new template and make exo:content property hidden by commenting lines 7-8 and uncommenting lines 5-6.	Template is edited successfully	Medium	CCP-1177 ECMS-3227
	REG_PLF308_ECMS_013	1.00	REG_PLF308_ECMS_013	Check Hidden Field's value is reset when editing a document	Step 5: Edit node in CE	Go back to site explorer, edit the node of step 3 and save.	Node is not edited	Medium	CCP-1177 ECMS-3227

## Bugs_v2_1_9
	TEST CASES					Passed	0	0	0	0
				Failed	0	0	0	0
	Function List:	Bugs on ECMS 2.1.9 for regression test					Blocked	0	0	0	0
	Total Main Cases:	12					Untested	0	0	0	0
				N/A	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
1.00	REG_PLF309_ECMS_001	1.00	REG_PLF309_ECMS_001	Check XSS with Navigation on URL	Step 1: Check XSS with Navigation on URL	- Go to acme home page / - input into the URL / http://localhost:8080/portal/public/acme/'-alert(1)-	No pop-up is shown	High	ECMS-3665 / CCP-1282	Pop-up is shown	nhung.vu
2.00	REG_PLF309_ECMS_002	1.00	REG_PLF309_ECMS_002	Check the displaying of content in CLV portlet	Step 1: Open form to set permission for folder	- Connect as root user / - Go to Acme website / - Open the Sites Explorer Portlet / - Go to collaboration/sites content/live/acme/documents / - Click on View Permission on action bar	Permission Management pop-up appear	High	ECMS-3694 / CCP-1292	The contents are not shown in public mode	nhung.vu
	REG_PLF309_ECMS_002	1.00	REG_PLF309_ECMS_002	Check the displaying of content in CLV portlet	Step 2: Set permission for folder	- Remove all permissions and keep only permissions for *:/platform/administrators group	Only users in *:/platform/administrators group can do action in this folder	High			nhung.vu
	REG_PLF309_ECMS_002	1.00	REG_PLF309_ECMS_002	Check the displaying of content in CLV portlet	Step 3: Create CLV page	- Open form to add new page / - Drag and drop Content List portlet into this page / - Click Edit icon of this portlet / - Choose: By Folder mode / - Point this CLV to display contents of folder collaboration/sites content/live/acme/documents / - Save	The contents are displayed	High			nhung.vu
	REG_PLF309_ECMS_002	1.00	REG_PLF309_ECMS_002	Check the displaying of content in CLV portlet	Step 4: View contents in edit mode	- Change to Edit mode	The contents are displayed	High			nhung.vu
3.00	REG_PLF309_ECMS_003	1.00	REG_PLF309_ECMS_003	Check XSS in Search portlet	Step 1: Check XSS in Search portlet	- Go to acme homepage / - Type some random words in Quick search box / - Go to address and edit the link to / Http://localhost:8080/portal/privat/acme/searchResult?portal=acme&keyword=<iframe src=http://ha.ckers.org/scriptlet.html <	No result found	High		The result is shown with iframe	nhung.vu
	REG_PLF309_ECMS_003	1.00	REG_PLF309_ECMS_003	Check XSS in Search portlet	Step 2: Check XSS in Search portlet	Chang the keyword= <button>Push my <strong>button</strong> baby</button>	No result found	High		The result is shown with button	nhung.vu
4.00	REG_PLF309_ECMS_004	1.00	REG_PLF309_ECMS_004	Check default value of Calendar field	Step 1: Open form to create new document	- Go to Content Explorer / - Select 1 drive / - Click Add Content in action bar to add new content	Form to add new content is shown	High	ECMS-3724 / CCP-1222	The current date/time is not shown	nhung.vu
	REG_PLF309_ECMS_004	1.00	REG_PLF309_ECMS_004	Check default value of Calendar field	Step 2: Check default value of Calendar field of Podcast document	- Choose template: Podcast	Current Date/Time is shown in Published field	High			nhung.vu
	REG_PLF309_ECMS_004	1.00	REG_PLF309_ECMS_004	Check default value of Calendar field	Step 3: Check default value of Calendar field of Sample node document	- Choose template: Sample node	Current Date/Time is shown in Date/Date time field	High			nhung.vu
5.00	REG_PLF309_ECMS_005	1.00	REG_PLF309_ECMS_005	Add new webcontent with java script	Step 1: Add new webcontent with java script	- Go to Content Explorer / - Open form to create new content / - Choose: Free layout webcontent / - Fill title and name / - Select Advanced Search tab / - Fill the javascript field with : alert("test"); / - Save and close	the webContent is displayed and the javascript is executed	High	ECMS-3420 / CCP-1224,		nhung.vu
6.00	REG_PLF309_ECMS_006	1.00	REG_PLF309_ECMS_006	Filter some actions insite nt: file	Step 1: Create new File content	- Go to Content Explorer / - Open form to create new content / - Choose: File / - Put values in required field / - Save	File is created successfully	High	ECMS-3534 / CCP-1252,		nhung.vu
	REG_PLF309_ECMS_006	1.00	REG_PLF309_ECMS_006	Filter some actions insite nt: file	Step 2: Filter some actions insite nt:file	- Select created file	In the action bar: there is no action: Add Folder, Add Content, Upload file, Import Node	High			nhung.vu
7.00	REG_PLF309_ECMS_006	2.00	REG_PLF309_ECMS_006	Filter some actions insite nt: file	Step 1:Upload new file	- Go to Content Explorer / - Upload new file	File is uploaded successfully successfully	High			nhung.vu
	REG_PLF309_ECMS_006	2.00	REG_PLF309_ECMS_006	Filter some actions insite nt: file	Step 2: Filter some actions insite nt:file	- Select uploaded file	In the action bar: there is no action: Add Folder, Add Content, Upload file, Import Node	High			nhung.vu
8.00	REG_PLF309_ECMS_007	1.00	REG_PLF309_ECMS_007	Check webDAV link	Step 1:Upload new file	- Go to Content Explorer / - Upload new file	File is uploaded successfully successfully	High	ECMS-3377 / CCP-1207	The link doesnot contains 'private'	nhung.vu
	REG_PLF309_ECMS_007	1.00	REG_PLF309_ECMS_007	Check webDAV link	Step 2: Check the webDAV link	- Right click on uploaded file and select Download And Allow Edition	The link should be shown: http://localhost:8080/rest/private/jcr/repository/collaboration ….	High			nhung.vu
9.00	REG_PLF309_ECMS_008	1.00	REG_PLF309_ECMS_008	Printing PDF	Step 1:Upload new PDF file	- Go to Content Explorer / - Upload new PFD file	File is uploaded successfully successfully	High	ECMS-3725 / CCP-1223	the content doesn't exist in the printed page	nhung.vu
	REG_PLF309_ECMS_008	1.00	REG_PLF309_ECMS_008	Printing PDF	Step 2: Publish file	- Select uploaded file above / - Click on Manage Publication in action bar / - Click on Publish	Uploaded file is published	High			nhung.vu
	REG_PLF309_ECMS_008	1.00	REG_PLF309_ECMS_008	Printing PDF	Step 3: Search PDF file	- Go to homepage of acme site / - Put uploaded file's name in the search box / - Press enter	Shows the result	High			nhung.vu
	REG_PLF309_ECMS_008	1.00	REG_PLF309_ECMS_008	Printing PDF	Step 4: Printing PDF file	- In search result list, open PDF file to view content / - Click on Print / - At the bottom of the page, you will find another "print", click on it and choose a page number, for example the first page	The header, footer and content of page are printed	High			nhung.vu
10.00	REG_PLF309_ECMS_009	1.00	REG_PLF309_ECMS_009	Check thumbnail view of PDF file	Step 1: Add thumbnail view for drive	- Go to Content Administration → Manage drive / - Add simple view for Site Management drive	Site Management drive is added new view	Medium	ECMS-3408 / CCP-1217	A black thumbnail	nhung.vu
	REG_PLF309_ECMS_009	1.00	REG_PLF309_ECMS_009	Check thumbnail view of PDF file	Step 2: Upload PDF file	- Go to Content Explorer / - Upload new PFD file	File is uploaded successfully successfully	Medium			nhung.vu
	REG_PLF309_ECMS_009	1.00	REG_PLF309_ECMS_009	Check thumbnail view of PDF file	Step 3: Check thumbnail view of PDF file	- Change to simple view	Thumbnail of PDF file is shown	Medium			nhung.vu
11.00	REG_PLF309_ECMS_010	1.00	REG_PLF309_ECMS_010	Check footer in IE9	Step 1:Upload new file	- Go to Content Explorer / - Upload new file with title: croix-rouge-francaise-lassociation-entend-combler-le-deficit-en-personnel-specialise-en-guyane	File is uploaded successfully successfully	Medium	ECMS-3492 / CCP-1237	the footer goes down	nhung.vu
	REG_PLF309_ECMS_010	1.00	REG_PLF309_ECMS_010	Check footer in IE9	Step 2: Check the footer	- Click on this document / - Move the mouse in the tree left banner	No UI error	Medium			nhung.vu
12.00	REG_PLF309_ECMS_011	1.00	REG_PLF309_ECMS_011	Check the SignIn portlet after edit	Step 1: Open form to edit content of SignIn portlet	- Log in / - Go to acme homepage / - Change to Edit mode / - Click Edit icon of Acme SignIn portlet	Form to edit content appear	Medium	ECMS-3436 / CCP-1224	Missing content: Welcome: (username)	nhung.vu
	REG_PLF309_ECMS_011	1.00	REG_PLF309_ECMS_011	Check the SignIn portlet after edit	Step 2: Edit content of SignIn portlet	- Add some characters in content / - Save and close / - Click on Publish in action bar	The content is published	Medium			nhung.vu
	REG_PLF309_ECMS_011	1.00	REG_PLF309_ECMS_011	Check the SignIn portlet after edit	Step 3: Check the displaying of new content	- Click on Back icon	The new content is shown.	Medium			nhung.vu

## Bug_v2_1_10
	TEST CASES					Passed	0	0	0	0
				Failed	0	0	0	0
	Function List:	Bugs on ECMS 2.1.10 for regression test					Blocked	0	0	0	0
	Total Main Cases:	3					Untested	0	0	0	0
				N/A	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
1.00	REG_PLF3010_ECMS_001	1.00	REG_PLF3010_ECMS_001	Delete content with accented name	Step 1: Create document with accented name	- Go to Content Explorer / - Select any drive / - Click on New Content in action bar / - Choose template: Article / - Put name: accentuée and title: accentuée / - Save	New document is created successfully	High	CCP-1323 / ECMS-3801
	REG_PLF3010_ECMS_001	1.00	REG_PLF3010_ECMS_001	Delete content with accented name	Step 2: Delete document	- RIght click on document above and select Delete	Document is deleted	High		Exception in console
2.00	REG_PLF3010_ECMS_002	1.00	REG_PLF3010_ECMS_002	Copy large files	Step 1: Create folders	- Go to Content Explorer / - Select any drive / - Click on New Folder in action bar / - Put folder's name and title / - Save / - Do this action again	2 folder are created successfully	High	ECMS-3696 / CCP-1294
	REG_PLF3010_ECMS_002	1.00	REG_PLF3010_ECMS_002	Copy large files	Step 2: Upload files	- Select 1 of 2 created folder above / - Click on Upload in action bar / - Upload 2 files: one is 120 MB, and another file whose size is small (less than a few kb).	2 files are uploaded successfully	High
	REG_PLF3010_ECMS_002	1.00	REG_PLF3010_ECMS_002	Copy large files	Step 3: Copy bigger file	- Right click on bigger file and select Copy / - Right click on the other folder and select Paste	The bigger file is copied	High
	REG_PLF3010_ECMS_002	1.00	REG_PLF3010_ECMS_002	Copy large files	Step 4: Copy smaller file	- Right click on smaller file and select Copy / - Right click on the other folder and select Paste	Only the smaller file is copied	High		Both smaller and bigger file are copied
3.00	REG_PLF3010_ECMS_003	1.00	REG_PLF3010_ECMS_003	Download file	Step 1: Download file	- Go to Content Explorer / - Select Site Management drive / - Select acme/documents folder / - Open Conditions and Requirements"(conditions.doc) doc / - Click on Download file / - Click Save in dialog	Get the expected office file, conditions.doc	High	ECMS-2071 / CCP-840	Get a "openit.lnk" file

## XSS
	TEST CASES					Passed	0	0	0	0
				Failed	0	0	0	0
	Function List:	Bugs XSS for regression test					Blocked	0	0	0	0
	Total Main Cases:	3					Untested	0	0	0	0
				N/A	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	- Login as mary	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
1.00	REG_XSS_ECMS_001	1.00	REG_XSS_ECMS_001	XSS vulnerability in tag's style	Step 1: Open form to add new tag's style	- Login as mary / - Go to Content Administration / - Go to Categories&Tags → Manage Tags / - Click on Add Style	Form to add new tag's style appears. This form has 3 fields: Style name, Document range and HTML style	High	ECMS-3826		nhung.vu
	REG_XSS_ECMS_001	1.00	REG_XSS_ECMS_001	XSS vulnerability in tag's style	Step 2: Check XSS	- Put valid value in name and document range field / - Put this script: <SCRIPT>alert(String.fromCharCode(88,83,83))</SCRIPT> into Html style field / - Click Update	New tag's style is created successfully	High		XSS message appears	nhung.vu
2.00	REG_XSS_ECMS_002	1.00	REG_XSS_ECMS_002	XSS vulnerability in Documents feature	Step 1: Upload document	- Login / - Go to Content Explorer / - Select any drive / - Click Upload in action bar / - Choose file to upload	File is uploaded successfully	High	ECMS-3853		nhung.vu
	REG_XSS_ECMS_002	1.00	REG_XSS_ECMS_002	XSS vulnerability in Documents feature	Step 2: Edit file	- Right click on uploaded file above and select Edit / - Put the script: <script>alert('boom ^^' + document.cookie)</script> in the title field / - Save	File is edited	High			nhung.vu
	REG_XSS_ECMS_002	1.00	REG_XSS_ECMS_002	XSS vulnerability in Documents feature	Step 3: Search file	- In quick search field, type some words from uploaded field	Show result is the uploaded field	High		XSS message appears	nhung.vu
3.00	REG_XSS_ECMS_003	1.00	REG_XSS_ECMS_003	Inject java script in Contact Us form	Step 1: Create new feedback	- Do not login / - Go to acme site / - Select Contact Us (Question) page / - Put <script>alert('java script executed')</script> into one of the textual input fields (for example field Your Name) / - Complete all required fields then click Send	The feedback is sent	High	ECMS-3961		nhung.vu
	REG_XSS_ECMS_003	1.00	REG_XSS_ECMS_003	Inject java script in Contact Us form	Step 2: Open the feedback	- Login as john / - Go to Content Explorer → Sites Management → acme → documents / - Open the new created feedback	The document is open to show content	High		java script gets executed.	nhung.vu

## Summary_Report
ECMS Regression Tests List				Total cases

Id	Functional Group	Functionality	Functionality Summary
Bugs_v2_1_4
REG_PLF304_ECMS_001	ECMS		Check life cycle in Manage Publications	1
REG_PLF304_ECMS_002	ECMS		Check Category validation	1
REG_PLF304_ECMS_003	ECMS		Check rss with special characters	1
REG_PLF304_ECMS_004	ECMS		Download attachment in Content Detail portlet	1
REG_PLF304_ECMS_005	ECMS		Check Content by URL page in public	1
REG_PLF304_ECMS_006	ECMS		Check Page Navigation in WCM Content Selector	1
REG_PLF304_ECMS_007	ECMS		Check multi-value WISIWYG field	1
Bugs_v2_1_5
REG_PLF305_ECMS_001	ECMS		Check Portuguese language translation of document	1
REG_PLF305_ECMS_002	ECMS		Check Duplicity Content Filter in CLV	1
REG_PLF305_ECMS_003	ECMS		Edit HTML in Content Explorer	1
REG_PLF305_ECMS_004	ECMS		Upload illustration image in free layout web content	1
REG_PLF305_ECMS_005	ECMS		Check form Select Category	1
REG_PLF305_ECMS_006	ECMS		Check long comment readability	1
REG_PLF305_ECMS_007	ECMS		Adding image in a content from CLV	1
REG_PLF305_ECMS_008	ECMS		Publish document in a locked folder	1
REG_PLF305_ECMS_009	ECMS		Check returned URL when navigated back to a CLV page after editing in Content Explorer	1
REG_PLF305_ECMS_010	ECMS		Check French Translation in Newsletter	1
REG_PLF305_ECMS_011	ECMS		Check French Translation in Content Explorer	1
REG_PLF305_ECMS_012	ECMS		Check WCM Content Selector in Chrome	1
REG_PLF305_ECMS_013	ECMS		Check FCK Editor in Chrome	1
REG_PLF305_ECMS_014	ECMS		Inject java script	1
REG_PLF305_ECMS_015	ECMS		Check multi value flag in View Node Properties	1
REG_PLF305_ECMS_016	ECMS		Upload a pdf file with user-input name	1
REG_PLF305_ECMS_017	ECMS		Manage Publications	1
Bugs_v2_1_6
REG_PLF306_ECMS_001	ECMS		Check limit of taxonomy length	1
REG_PLF306_ECMS_002	ECMS		Check RTF Document Edition Dialog	1
REG_PLF306_ECMS_003	ECMS		Check server start-up with specified language	1
REG_PLF306_ECMS_004	ECMS		Check permission removal on document	1
REG_PLF306_ECMS_005	ECMS		Edit metadata with multi-value	1
REG_PLF306_ECMS_006	ECMS		Search and download file of which name contain apostrophe ( character ' )	1
REG_PLF306_ECMS_007	ECMS		Check page navigation in File Explorer	1
REG_PLF306_ECMS_008	ECMS		Check content sort order in CLV	1
REG_PLF306_ECMS_009	ECMS		Check Portuguese translation	1
REG_PLF306_ECMS_010	ECMS		Check Edit form of a File document	1
REG_PLF306_ECMS_011	ECMS		Check link in WYSIWYG field	1
REG_PLF306_ECMS_012	ECMS		Check 'Add Translation' with Simplified Chinese	1
REG_PLF306_ECMS_013	ECMS		Check Space Document	2
REG_PLF306_ECMS_014	ECMS		Check Group drives	1
REG_PLF306_ECMS_015	ECMS		Check Manage Publication Panel template	0
Bugs_v2_1_7
REG_PLF307_ECMS_001	ECMS		"View Properties" Component	1
REG_PLF307_ECMS_002	ECMS		Replacing a file in categories	1
REG_PLF307_ECMS_003	ECMS		Selecting the 'workflow' publication workflow	1
REG_PLF307_ECMS_004	ECMS		Images in ACME Site	2
REG_PLF307_ECMS_005	ECMS		*, ~, +, - characters in simple search and advanced search	1
REG_PLF307_ECMS_006	ECMS		Linked documents of article is click-able in a SCV page	1
REG_PLF307_ECMS_007	ECMS		Check the displaying of Content based on custom node type a CLV page	1
REG_PLF307_ECMS_008	ECMS		Check right URL when in put title of node with specical characters in IE 7 and IE 8	1
REG_PLF307_ECMS_009	ECMS		Check search result with keyword in comment of document	1
REG_PLF307_ECMS_010	ECMS		Check the displaying of Content explorer portlet in 'level3' page	1
REG_PLF307_ECMS_011	ECMS		Check that Double left click on a node works properly in Chrome	1
REG_PLF307_ECMS_012	ECMS		Check delete Favorites folder in Private Drive of user	1
REG_PLF307_ECMS_013	ECMS		Check "Add/Manage Content" actions from CLV in "Dynamic Navigation" active mode	1
REG_PLF307_ECMS_014	ECMS		Check load icon in Simple View	1
REG_PLF307_ECMS_015	ECMS		Check java.util.MissingResourceException when try to open a PDF file.	1
REG_PLF307_ECMS_016	ECMS		Check: delete a node of a workspace different from trash one's	1
REG_PLF307_ECMS_017	ECMS		Check: Shared css and js is reloaded after server restart	1
REG_PLF307_ECMS_018	ECMS		A node that don't point to a page does not have a link on Navigation portlet	1
REG_PLF307_ECMS_019	ECMS		Setting a content Explorer with parameterize option	1
Bugs_v2_1_8				0
REG_PLF308_ECMS_001	ECMS		Check whether unknown error appears when do action on document while trying to edit	1
REG_PLF308_ECMS_002	ECMS		Create and delete javascript files from Content Explorer	1
REG_PLF308_ECMS_003	ECMS		Check name is automatically generated when creating a new content	1
REG_PLF308_ECMS_004	ECMS		Check whether Uploaded image gets overwritten	1
REG_PLF308_ECMS_005	ECMS		Check Search results are displayed 10 items per page	1
REG_PLF308_ECMS_006	ECMS		Check displaying of Content Explorer portlet in home page	1
REG_PLF308_ECMS_007	ECMS		Click on "View document" in a space	1
REG_PLF308_ECMS_008	ECMS		Check applying two filters in the Filter By Type of File Explorer	1
REG_PLF308_ECMS_009	ECMS		Check the results of an initial research is cleared during a second search	1
REG_PLF308_ECMS_010	ECMS		Searching under a category in Sites Explorer	3
REG_PLF308_ECMS_011	ECMS		Check nullPointerException when Setting a name to taxonomyAction	1
REG_PLF308_ECMS_012	ECMS		Check displaying HTM Lists in exo content.	1
REG_PLF308_ECMS_013	ECMS		Check Hidden Field's value is reset when editing a document	1
Bugs_v2_1_9				0
REG_PLF309_ECMS_001	ECMS		Check XSS with Navigation on URL	1
REG_PLF309_ECMS_002	ECMS		Check the displaying of content in CLV portlet	1
REG_PLF309_ECMS_003	ECMS		Check XSS in Search portlet	1
REG_PLF309_ECMS_004	ECMS		Check default value of Calendar field	1
REG_PLF309_ECMS_005	ECMS		Add new webcontent with java script	1
REG_PLF309_ECMS_006	ECMS		Filter some actions insite nt: file	2
REG_PLF309_ECMS_007	ECMS		Check webDAV link	1
REG_PLF309_ECMS_008	ECMS		Printing PDF	1
REG_PLF309_ECMS_009	ECMS		Check thumbnail view of PDF file	1
REG_PLF309_ECMS_010	ECMS		Check footer in IE9	1
REG_PLF309_ECMS_011	ECMS		Check the SignIn portlet after edit	1
Bugs_v2_1_10
REG_PLF3010_ECMS_001	ECMS		Delete content with accented name	1
REG_PLF3010_ECMS_002	ECMS		Copy large files	1
REG_PLF3010_ECMS_003	ECMS		Download file	1
XSS
REG_XSS_ECMS_001	ECMS		XSS vulnerability in tag's style	1
REG_XSS_ECMS_002	ECMS		XSS vulnerability in Documents feature	1
REG_XSS_ECMS_003	ECMS		Inject java script in Contact Us form	1

Total				92