## Cover
PLF-SOC REGRESSION TEST CASES
Version:	1.4
Issue date:	24-May-2012
Product Name:	Social
Project Name:	SOC
Module:	Regression
Total Cases:	15
Test Status:	Passed: Test is OK / Blocked: Could not run the test (another bug is blocking) / Failed: Test failed, a bug is entered on it (please add the bug ID) / N/A: Test is not possible to run on this version

Record of change:
Effective Date	Version	Change description	Originator	Reviewer/ / Approver	Reference
6-Oct-2011	1.0	Create new test file: Bugs_v1_1_6 sheet	Hanh.Ly
7-Oct-2011	1.1	Create Bugs_v1_1_5 sheet	Hanh.Ly
10-Oct-2011	1.2	Create Bugs_v1_1_4 sheet	Hanh.Ly
27-Dec-2011	1.3		Nhung.Vu
24-My-2012	1.4	Create Bugs_v1_1_9 sheet	Hang.Nguyen

## Check_List
Check List / Based on Product built version: SOC 1.1.x		Priority	Check List / Based on Product built version:	Check List / Based on Product built version:
Id	Main cases	Priority	Selenium	Table of record
v1_1_6				Total of High	0
REG_PLF306_SOC_001.001	Check activities after delete connection	High		Total of Medium	0
REG_PLF306_SOC_002.001	Access space has the same name with page at the root path	High		Total of Low	0
REG_PLF306_SOC_002.002	Access page has the same name with space	High
V1_1_5
REG_PLF305_SOC_001.001	Check the displaying of space in My Space menu	Medium
REG_PLF305_SOC_002.001	Check activities when change date time	High
REG_PLF305_SOC_003.001	Check the spelling in French message of connection request	Low
REG_PLF305_SOC_004.001	Delete default application on space	High
REG_PLF305_SOC_005.001	Check avatar of admin in space	High
REG_PLF305_SOC_006.001	Check Space setting tab by user is non-moderator	Medium
REG_PLF305_SOC_007.001	Share link while add activity
V1_1_4
REG_PLF304_SOC_001.001	Check Use name instead of login for connection activities	High
REG_PLF304_SOC_002.001	Check activities of connecting user	High
REG_PLF304_SOC_002.001	Accepting invitation clears the list	High
V1_1_7
REG_PLF307_SOC_001	Check intranet Homepage after change language into French	Medium
REG_PLF307_SOC_002	Check displaying of space's information after change language into French	Medium

V1_1_8
REG_PLF308_SOC_001	Check View doc on a space	High
REG_PLF308_SOC_002	Check invite member whose name contains "-" to a private space	High
REG_PLF308_SOC_003	Check when sharing an activity within an empty activity stream	Medium
V1_1_9
REG_PLF309_SOC_001	Possible XSS attack by adding new activity stream	High
REG_PLF308_SOC_002	Check add a post or an answer that contains some characters	High
REG_PLF308_SOC_003	Check display in activity stream when click Like button	Medium

## Bugs_v1_1_4
	TEST CASES					Passed	0	0	0	0	0	0	0
				Failed	0	0	0	0	0	0	0
	Function List:	Bugs on SOC 1.1.4 for regression test					Blocked	0	0	0	0	0	0	0
	Total Main Cases:	3					Untested	0	0	0	0	0	0	0
				N/A	0	0	0	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
1.00	REG_PLF304_SOC_001	1.00	REG_PLF304_SOC_001	Check Use name instead of login for connection activities	Step 1: Demo send connection request for John	- Log in by demo / - Move mouse to user's name and select Find People / - Click on icon to invite John	An invitation is sent to John	High	SOC-1519 / CCP-804	Show message "demo is now connected with john"	thao.pham
	REG_PLF304_SOC_001	1.00	REG_PLF304_SOC_001	Check Use name instead of login for connection activities	Step 2: Check the invitation of John	- Log in by john / - Click on My Status button	Show message: Jack Miller invited you to connect. Accept | Refuse	High			thao.pham
	REG_PLF304_SOC_001	1.00	REG_PLF304_SOC_001	Check Use name instead of login for connection activities	Step 3: Accept connection	Click on Accept link	Show message:You are now connected with Jack Miller.	High			thao.pham
2.00	REG_PLF304_SOC_002	1.00	REG_PLF304_SOC_002	Check activities of connecting user	Step 1: Create new space	- Go to /portal/public/intranet / - Login by demo / - Click on My Spaces / - Put space's name / - Click on Create	New space is created successfully	High	SOC-1517 / CCP-806	user can NOT see activities shared by people belonging to his network even in private spaces	thao.pham
	REG_PLF304_SOC_002	1.00	REG_PLF304_SOC_002	Check activities of connecting user	Step 2: Create activities	- Select new space above / - Add some activites	Activities is added successfully	High			thao.pham
	REG_PLF304_SOC_002	1.00	REG_PLF304_SOC_002	Check activities of connecting user	Step 3: Add connection	- Move mouse to user's name and select Find People / - Add connect with Mary	A request is sent to Mary	High			thao.pham
	REG_PLF304_SOC_002	1.00	REG_PLF304_SOC_002	Check activities of connecting user	Step 4: Check the invitation	- Log in as Mary / - Select My Status button / - Click on Accept button link	Mary and Demo is friend	High			thao.pham
	REG_PLF304_SOC_002	1.00	REG_PLF304_SOC_002	Check activities of connecting user	Step 5: Check the activities created by demo	- Click on Connection button	Activities create by demo are shown	High			thao.pham
3.00	REG_PLF304_SOC_003	1.00	REG_PLF304_SOC_003	Accepting invitation clears the list	Step 1: Add connect to Demo from Root	- Log in by Root / - Move mouse to user's name and select Find People / - Add connect with Demo	A request is sent to Demo	High	SOC-1455 / CCP-757	Accepting an invitation clears the connection list	thao.pham
	REG_PLF304_SOC_003	1.00	REG_PLF304_SOC_003	Accepting invitation clears the list	Step 2: Add connect to Demo from John	- Log in by Mary / - Move mouse to user's name and select Find People / - Add connect with Demo	A request is sent to Demo	High			thao.pham
	REG_PLF304_SOC_003	1.00	REG_PLF304_SOC_003	Accepting invitation clears the list	Step 3: Add connect to Demo from Mary	- Log in by Mary / - Move mouse to user's name and select Find People / - Add connect with Demo	A request is sent to Demo	High			thao.pham
	REG_PLF304_SOC_003	1.00	REG_PLF304_SOC_003	Accepting invitation clears the list	Step 4: Accept connection	- Log in by Demo / - Click on My Status / - Accept the connection from Root, John	Demo is a friend of Root, john	High			thao.pham
	REG_PLF304_SOC_003	1.00	REG_PLF304_SOC_003	Accepting invitation clears the list	Step 5: Restart server	- Restart server to clear cached	Server is restarted	High			thao.pham
	REG_PLF304_SOC_003	1.00	REG_PLF304_SOC_003	Accepting invitation clears the list	Step 6: Accept connection	- Log in by Demo / - Click on My Network → Incomming / - Accept the connection from Mary	Demo is a friend of Mary	High			thao.pham
	REG_PLF304_SOC_003	1.00	REG_PLF304_SOC_003	Accepting invitation clears the list	Step 7: Check friend list	- Click on My Network	Root, John, Mary is listed	High			thao.pham

## Bugs_v1_1_5
	TEST CASES					Passed	0	0	0	0	0	0	0
				Failed	0	0	0	0	0	0	0
	Function List:	Bugs on SOC 1.1.5 for regression test					Blocked	0	0	0	0	0	0	0
	Total Main Cases:	7					Untested	0	0	0	0	0	0	0
				N/A	0	0	0	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
1.00	REG_PLF305_SOC_001	1.00	REG_PLF305_SOC_001	Check the displaying of space in My Space menu	Step 1: Create new space	- Go to /portal/public/intranet / - Login by root / - Click on My Spaces / - Put space's name / - Click on Create	New space is created successfully	Medium	SOC-1780 / CCP-837	Don't update new space on menu
	REG_PLF305_SOC_001	1.00	REG_PLF305_SOC_001	Check the displaying of space in My Space menu	Step 2: Check the displaying of new space	Move mouse on My Spaces	New space is listed on My Spaces menu	Medium
2.00	REG_PLF305_SOC_002	1.00	REG_PLF305_SOC_002	Check activities when change date time	Step 1: Create new space	- Go to /portal/public/intranet / - Login by root / - Click on My Spaces / - Create 2 space: AAA and BBB	New spaces are created successfully	High	SOC-1774 / CCP-955	Activities of spaces are not well sorted
	REG_PLF305_SOC_002	1.00	REG_PLF305_SOC_002	Check activities when change date time	Step 2: Add activities for space	- Select space AAA / - Add some activities in this space / - Select space BBB / - Add some activities in this space	Activities are created	High
	REG_PLF305_SOC_002	1.00	REG_PLF305_SOC_002	Check activities when change date time	Step 3: Invite user to space	- Select space AAA / - Click on Space Setting tab / - Click on Member tab / - Invite 1 user to join this space (demo)	Invited user is listed on Invited table	High
	REG_PLF305_SOC_002	1.00	REG_PLF305_SOC_002	Check activities when change date time	Step 4: Accept invitation by invited user	- Log in by demo / - Select My Spaces → Invitation / - Click on Accept icion to join space	The invitation to join space is disappeared. The message “Jack Miller has joined” on space AAA	High
	REG_PLF305_SOC_002	1.00	REG_PLF305_SOC_002	Check activities when change date time	Step 5: Add activities by invited user	- Select space AAA / - Add some activities	Activities are created by demo	High
	REG_PLF305_SOC_002	1.00	REG_PLF305_SOC_002	Check activities when change date time	Step 6: Change date time of server	- Change the date time of your computer / - Restart the server	Date time of server is changed	High
	REG_PLF305_SOC_002	1.00	REG_PLF305_SOC_002	Check activities when change date time	Step 7: Add comment by invited user	- Log in by demo / - Add comments in activites	Comments are added	High
	REG_PLF305_SOC_002	1.00	REG_PLF305_SOC_002	Check activities when change date time	Step 8: Check activities after change date time of server	- Refresh browser	Activities of spaces are well sorted	High
3.00	REG_PLF305_SOC_003	1.00	REG_PLF305_SOC_003	Check the spelling in French message of connection request	Step 1: Add a contact	- Change the language to French / - Login as john / - Go to Mon Réseau/Sortant/Ajouter des Contacts / - Invite Mary Williams	Invitation is sent	Low	SOC-1481 / CCP-894	The message is : john vous a envoyé une demande de connxion.
	REG_PLF305_SOC_003	1.00	REG_PLF305_SOC_003	Check the spelling in French message of connection request	Step 2: Check the invitation	- Log in by Mary / - Go to Mes Activités/Mon status	Show message: john vous a envoyé une demande de connexion.	Low
4.00	REG_PLF305_SOC_004	1.00	REG_PLF305_SOC_004	Delete default application on space	Step 1: Create new space	- Go to /portal/public/intranet / - Login / - Click on My Spaces / - Put space's name / - Click on Create	New space is created successfully	High	SOC-1460 / CCP-841	Unknown error
	REG_PLF305_SOC_004	1.00	REG_PLF305_SOC_004	Delete default application on space	Step 2: Select new space	- Access new space / - Click on Space Setting tab / - Click on Application / - Click Delete icon on default application: calendar, forum, answers...	Application is deleted successfully. It is not listed on the left pane of space	High
5.00	REG_PLF305_SOC_005	1.00	REG_PLF305_SOC_005	Check avatar of admin in space	Step 1: Create new space	- Go to /portal/public/intranet / - Login by john / - Click on My Spaces / - Put space's name / - Click on Create	New space is created successfully	High	SOC-1406 / CCP-830	The avatars of all admin are the same
	REG_PLF305_SOC_005	1.00	REG_PLF305_SOC_005	Check avatar of admin in space	Step 2: Invite users to space	- Select new space / - Invite user to join this space:demo	Users are listed on Invited table	High
	REG_PLF305_SOC_005	1.00	REG_PLF305_SOC_005	Check avatar of admin in space	Step 3: Accept the invitation	- Login by user are invited at step 1 / - Click on My Spaces in navigation bar / - Click on Invitation / - Accept the invitation	The invitation to join space is disappeared.	High
	REG_PLF305_SOC_005	1.00	REG_PLF305_SOC_005	Check avatar of admin in space	Step 4: Approve user to admin of space	- Login by john / - Select new space / - Click on Space Setting → Member / - Click on Make Leader icon on invited user	Invited user become the admin of this space	High
	REG_PLF305_SOC_005	1.00	REG_PLF305_SOC_005	Check avatar of admin in space	Step 5: Add avatar for space creator	- Login by john / - Move mouse to user's name at the top-right and select My Profile / - Click on Change Avatar link / - Browse an image file and click on Confirm button	Space creator has new avatar	High
	REG_PLF305_SOC_005	1.00	REG_PLF305_SOC_005	Check avatar of admin in space	Step 6: Change avatar of	- Log in by demo / - Move mouse to user's name at the top-right and select My Profile / - Click on Change Avatar link / - Browse an image file (not the same with space creator) and click on Confirm button	Demo has new avatar	High
	REG_PLF305_SOC_005	1.00	REG_PLF305_SOC_005	Check avatar of admin in space	Step 7: Check the displaying of admin's avatar	Select new space	Avatar of admins in space is difference	High
6.00	REG_PLF305_SOC_006	1.00	REG_PLF305_SOC_006	Check Space setting tab by user is non-moderator	Step 1: Create new space	- Go to /portal/public/intranet / - Login by john / - Click on My Spaces / - Put space's name / - Click on Create	New space is created successfully	Medium	SOC-1575 / CCP-831	Normal user can see space setting tab
	REG_PLF305_SOC_006	1.00	REG_PLF305_SOC_006	Check Space setting tab by user is non-moderator	Step 2: Invite users to space	- Select new space / - Invite user to join this space:demo	Users are listed on Invited table	Medium
	REG_PLF305_SOC_006	1.00	REG_PLF305_SOC_006	Check Space setting tab by user is non-moderator	Step 3: Accept the invitation	- Login by user are invited at step 1 / - Click on My Spaces in navigation bar / - Click on Invitation / - Accept the invitation	The invitation to join space is disappeared.	Medium
	REG_PLF305_SOC_006	1.00	REG_PLF305_SOC_006	Check Space setting tab by user is non-moderator	Step 4: Check the displaying of Space	- Still log in with demo / - Select new space	Space Setting tab is not displayed	Medium
7.00	REG_PLF305_SOC_007	1.00	REG_PLF305_SOC_007	Share link while add activity	Step 1: Create new space	- Go to /portal/public/intranet / - Login by john / - Click on My Spaces / - Put space's name / - Click on Create	New space is created successfully	High	SOC-1581 / CCP-849	Unable to share links when clicking attach button
	REG_PLF305_SOC_007	1.00	REG_PLF305_SOC_007	Share link while add activity	Step 2: Share link while add activity	- Go to home page of space / - Click on Share Link icon / - Enter an http or https link in attach link form / - Click Attach	Link is shared	High

## Bugs_v1_1_6
	TEST CASES					Passed	0	0	0	0	0	0	0
				Failed	0	0	0	0	0	0	0
	Function List:	Bugs on SOC 1.1.6 for regression test					Blocked	0	0	0	0	0	0	0
	Total Main Cases:	3					Untested	0	0	0	0	0	0	0
				N/A	0	0	0	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
1.00	REG_PLF306_SOC_001	1.00	REG_PLF306_SOC_001	Check activities after delete connection	Step 1: Create activities by demo	- Go to intranet portal / - Login as demo / - Create some activities	Activities is created successfully	High	SOC-1733 / CCP-927	Error when go to My activities
	REG_PLF306_SOC_001	1.00	REG_PLF306_SOC_001	Check activities after delete connection	Step 2: Connect with demo by mary	- Login as mary / - Move mouse over user's name and select Find People / - Connect with demo	Waiting for demo accept connection	High
	REG_PLF306_SOC_001	1.00	REG_PLF306_SOC_001	Check activities after delete connection	Step 3: Demo accept connection	- Login as demo / - Go to My network/Incomming(Receipt Invitation) / - Accept connection / - Select My Activities	A message is shown: Jack Miller is now connected with Mary Williams.	High
	REG_PLF306_SOC_001	1.00	REG_PLF306_SOC_001	Check activities after delete connection	Step 4: Delete user	- Login as root / - Go to User and Group Manager / - Select User Management / - Delete Mary	Mary is deleted	High
	REG_PLF306_SOC_001	1.00	REG_PLF306_SOC_001	Check activities after delete connection	Step 5: Check activities	- Login as demo / - Select My activities	No exception	High
2.00	REG_PLF306_SOC_002	1.00	REG_PLF306_SOC_002	Access space has the same name with page at the root path	Step 1: Create a page at the root path	- Go to portal/private/intranet link / - Click on Site Editor → Add New page / - Select the root path / - Put node name: Test / - Fill values in next steps / - Click Finish	New page named Test is created successfully	High	SOC-1753 / CCP-938	Space is created successfully. When access the space, content of page is shown
	REG_PLF306_SOC_002	1.00	REG_PLF306_SOC_002	Access space has the same name with page at the root path	Step 2: Create new space has the same name with page above	- Click on My Spaces / - Click Add new space button / - Put space name has the same with page above	Show message alert that you can not create a space has the same name with page in the same destination	High
3.00	REG_PLF306_SOC_002	2.00	REG_PLF306_SOC_002	Access page has the same name with space	Step 1: Create a space	- Click on My Spaces / - Click Add new space button / - Put space name: Test / - Click on Create	Space is created successfully	High
	REG_PLF306_SOC_002	2.00	REG_PLF306_SOC_002	Access page has the same name with space	Step 2: Create new page in the root path has the same name with space	- Go to portal/private/intranet link / - Click on Site Editor → Add New page / - Select the root path / - Put node name: Test / - Fill values in next steps / - Click Finish	Show message alert that you can not create a page has the same name with space	High

## Bugs_v1_1_7
	TEST CASES					Passed	0	0	0	0	0	0	0
				Failed	0	0	0	0	0	0	0
	Function List:	Bugs on SOC 1.1.7 for regression test					Blocked	0	0	0	0	0	0	0
	Total Main Cases:	2					Untested	0	0	0	0	0	0	0
				N/A	0	0	0	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
1.00	REG_PLF307_SOC_001	1.00	REG_PLF307_SOC_001	Check intranet Homepage after change language into French	Step 1: Check Homepage	- Go to intranet portal / - Login as demo / - Move mouse to Jack Miller / - Click Change Language / - Select French > click button Apply	- Homepage is well translated in French / + Button Connections is Mes connexions / + Button Spaces is Mes espaces / + Button My Status is Mon statut	Medium	SOC-2057 / CCP-1087 / SOC-1969 / CCP-1130	Some labels of Contact View, User Activities are not translated to french	thao.pham
	REG_PLF307_SOC_001	1.00	REG_PLF307_SOC_001	Check My Activities after change language into French	Step 2: Check My Activities	- Move mouse to Jack Miller / - Click My Activities	- My Activities page is well translated in French / + Button Connections is Mes connexions / + Button Spaces is Mes espaces / + Button My Status is Mon statut	Medium	SOC-2057 / CCP-1087 / SOC-1969 / CCP-1130	Some labels of Space, Space Settings, Space Navigation, Add Contact, Find People are not translated to French	thao.pham
	REG_PLF307_SOC_001	1.00	REG_PLF307_SOC_001	Check Find People after change language into French	Step 3: Check Find People	- Move mouse to Jack Miller / - Click on Find People / - Click on M character / - Click on Mary Williams	- Find People page is well translated in French / + All is Tous / + Gender is Sexe / - Activities page is well translated in French / + User Activities is Les activités d'utilisateur / + Display a line "Il n'y a aucune activité."	Medium	SOC-2057 / CCP-1087 / SOC-1969 / CCP-1130		thao.pham
	REG_PLF307_SOC_001	1.00	REG_PLF307_SOC_001	Check Profile after change language into French	Step 4: Check Profile	- Click on Profil of Mary Williams	- My Profile page is well translated in French / + Content of Contact section is "Mary n'a pas encore saisi d'information de contact"	Medium	SOC-2057 / CCP-1087 / SOC-1969 / CCP-1130		thao.pham
	REG_PLF307_SOC_001	1.00	REG_PLF307_SOC_001	Check Contacts after change language into French	Step 5: Check Connections	- Click on Contacts of Mary Williams	- My Network page is well translated in French / + All is Tous / + Mary's CONNECTIONS is Les contacts de Mary / + Gender is Sexe	Medium	SOC-2057 / CCP-1087 / SOC-1969 / CCP-1130		thao.pham
2.00	REG_PLF307_SOC_002	1.00	REG_PLF307_SOC_002	Check displaying of space's information after change language into French	Step 1: Create a Space	- Login as demo / - Click My Spaces > Find Spaces / - Click Add New Spaces / - Input valid all value with name is Space1 / - Click Save	- Space1 is created and shown in Space lists	Medium	SOC-2057 / CCP-1087 / SOC-1969 / CCP-1130		thao.pham
	REG_PLF307_SOC_002	1.00	REG_PLF307_SOC_002	Check displaying of space's information after change language into French	Step 2: Change Language	- Move mouse to Jack Miller / - Click Change Language / - Select French > click button Apply	- Language is set into French	Medium	SOC-2057 / CCP-1087 / SOC-1969 / CCP-1130		thao.pham
	REG_PLF307_SOC_002	1.00	REG_PLF307_SOC_002	Check displaying of space's information after change language into French	Step 3: Check Find Space	- Click on Trouver des Espaces	- Find Space page is well translated in French / - Spaces Found is Espaces trouvés	Medium			thao.pham
	REG_PLF307_SOC_002	1.00	REG_PLF307_SOC_002	Check displaying of space's information after change language into French	Step 4: Check Like	- Click on Space1 in Space list / - Click on J'aime of demo's post / - Click on J'aime of mary's post	- Home page of Space1 is well translated in French / - Display Vous aimez ça. / - Display 1 persone Vous aimez ça.	Medium	SOC-2057 / CCP-1087 / SOC-1969 / CCP-1130		thao.pham
	REG_PLF307_SOC_002	1.00	REG_PLF307_SOC_002	Check displaying of space's information after change language into French	Step 5: Check Settings	- Click on Space Settings	- Settings page is well translated in French	Medium	SOC-2057 / CCP-1087 / SOC-1969 / CCP-1130		thao.pham
	REG_PLF307_SOC_002	1.00	REG_PLF307_SOC_002	Check displaying of space's information after change language into French	Step 6: Check Visibility	- Select Visibilité tab	- Visibility page is well translated in French / + Visible is Visible / + Hidden is Masqué / + Open is Ouvert / + Validation is Validation / + Close is Fermé	Medium	SOC-2057 / CCP-1087 / SOC-1969 / CCP-1130		thao.pham
	REG_PLF307_SOC_002	1.00	REG_PLF307_SOC_002	Check displaying of space's information after change language into French	Step 7: Check Members	- Select Membres tab	- Members page is well translated in French / - Tool-tip of Invite icon is Inviter	Medium	SOC-2057 / CCP-1087 / SOC-1969 / CCP-1130		thao.pham
	REG_PLF307_SOC_002	1.00	REG_PLF307_SOC_002	Check displaying of space's information after change language into French	Step 8: Check Applications	- Select Applications tab	- Applications page is well translated in French	Medium	SOC-2057 / CCP-1087 / SOC-1969 / CCP-1130		thao.pham
	REG_PLF307_SOC_002	1.00	REG_PLF307_SOC_002	Check displaying of space's information after change language into French	Step 9: Check Space Navigation	- Select Navigation d'espace tab	- Space Navigation page is well translated in French	Medium	SOC-2057 / CCP-1087 / SOC-1969 / CCP-1130		thao.pham

## Bugs_v1_1_8
	TEST CASES					Passed	0	0	0	0	0	0	0
				Failed	0	0	0	0	0	0	0
	Function List:	Bugs on SOC 1.1.8 for regression test					Blocked	0	0	0	0	0	0	0
	Total Main Cases:	3					Untested	0	0	0	0	0	0	0
				N/A	0	0	0	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
1.00	REG_PLF308_SOC_001	1.00	REG_PLF308_SOC_001	Check View doc on a space	Step 1: Add new space	- Go to intranet portal / - Login portal / - Go to My space / - Add new space	- Add new space successfully	High	SOC-2018 / CCP-1063	Click on "View document" in a space redirects you to the space's home page	thao.pham
	REG_PLF308_SOC_001	1.00	REG_PLF308_SOC_001	Check View doc on a space	Step 2: Upload a document	- Go to documents page in a space / - Click upload icon and upload a document	- Upload document successfully	High			thao.pham
	REG_PLF308_SOC_001	1.00	REG_PLF308_SOC_001	Check View doc on a space	Step 3: View Document	- Right on document and and choose "View document"	- The content of document is displayed	High			thao.pham
2.00	REG_PLF308_SOC_002	1.00	REG_PLF308_SOC_002	Check invite member whose name contains "-" to a private space	Step 1: Add new user	- Login by root / - Go to add new user / - Add user with name: “dupont-p”	- New user is added successfully	High	SOC-2239 / CCP-1140	can't invite member whose name contains "-" to a private space	thao.pham
	REG_PLF308_SOC_002	1.00	REG_PLF308_SOC_002	Check invite member whose name contains "-" to a private space	Step 2: Add new space private with name “test 2”	- Go to My Space / - Click Add new space / - Add new space private with name “test” ( In Visibility tab choose: Check “Visible” and “Close”)	- Add new space successfully	High			thao.pham
	REG_PLF308_SOC_002	1.00	REG_PLF308_SOC_002	Check invite member whose name contains "-" to a private space	Step 3: Invite new user into space	- Open space / - Go to Space setting / - Choose member tab / - Select new user which added at step 1 / - Click Add	- New user is added successfully	High			thao.pham
3.00	REG_PLF308_SOC_003	1.00	REG_PLF308_SOC_003	Check when sharing an activity within an empty activity stream	Step 1: Add new space	- Go to intranet portal / - Login portal / - Go to My space / - Add new space	- Add new space successfully	Medium	SOC-2350 / CCP-1169	Error when sharing an activity within an empty activity stream	thao.pham
	REG_PLF308_SOC_003	1.00	REG_PLF308_SOC_003	Check when sharing an activity within an empty activity stream	Step 2: Delete all the messages in the activity stream	- Open space / - Delete all the messages in the activity stream (like user has just created space)	The following text is shown under the activitystream "Not any updates posted yet."	Medium			thao.pham

## Bugs_v1_1_9
	TEST CASES					Passed	0	0	0	0	0	0	0
				Failed	0	0	0	0	0	0	0
	Function List:	Bugs on SOC 1.1.9 for regression test					Blocked	0	0	0	0	0	0	0
	Total Main Cases:	4					Untested	0	0	0	0	0	0	0
				N/A	0	0	0	0	0	0	0
Case No	Related function	Case ID	Path	Case Description	Step Description	Steps to produce	Expected Output	Priority	Link	Bug description	Tester	IE7	FireFox3.5	Comment/Bug
1.00	REG_PLF309_SOC_001	1.00	REG_PLF309_SOC_001	Possible XSS attack by adding new activity stream	Step 1: Attack link by XSS	- Go to intranet portal / - Login portal / - Go to Social Intranet Homepage / - Click attack link and paste : Paste a valid URL. Click [Attach] button / - Paste this: <script>alert('XSS');</script> in the text field / - Click [Share] button	- Attach a link successfully / - Share link is OK and show title is XSS	High	SOC-2588 / CCP-1243	Possible XSS attack by adding new activity stream	thao.pham
2.00	REG_PLF308_SOC_002	1.00	REG_PLF308_SOC_002	Check add a post or an answer that contains some characters	Step 1: Add new space	- Add new space	- Add new space successfully	High	SOC-2589 / CCP-1261	Some characters and spaces are not formatted in activity stream	thao.pham
	REG_PLF308_SOC_002	1.00	REG_PLF308_SOC_002	Check add a post or an answer that contains some characters	Step 2: add a post or an answer that contains some characters	- Go to Forum in this space / - Create a topic / - Add a post like this: Test post contains é or è or & or ....	- The content of document is displayed	High			thao.pham
	REG_PLF308_SOC_002	1.00	REG_PLF308_SOC_002	Check add a post or an answer that contains some characters	Step 3: Check on activity stream	- Go to Acitivy	- The post is displayed well	High			thao.pham
3.00	REG_PLF308_SOC_003	1.00	REG_PLF308_SOC_003	Check display in activity stream when click Like button with Arabic language	Step 1: Add new space with Arabic language	- Change language to Arabic / - Go to My Space / - Click Add new space with Arabic name	- Add new space successfully	Medium	SOC-2532 / CCP-1220		thao.pham
	REG_PLF308_SOC_003	1.00	REG_PLF308_SOC_003	Check display in activity stream when click Like button with Arabic language	Step 2: Check display when click like/unlike button	- Go to homepage of new space / - Click Like/unlike button in activity stream	The characters in the space name display well	Medium			thao.pham
4.00	REG_PLF308_SOC_003	2.00	REG_PLF308_SOC_003	Check display in activity stream when click Like button with French language	Step 1: Add new space with French language	- Change language to French / - Go to My Space / - Click Add new space with French name "espace testé à la plage"	- Add new space successfully	Medium			thao.pham
	REG_PLF308_SOC_003	2.00	REG_PLF308_SOC_003	Check display in activity stream when click Like button with French language	Step 2: Check display when click like/unlike button	- Go to homepage of new space / - Click Like/Unlike button in activity stream	The characters in the space name display well	Medium			thao.pham

## Summary_Report
SOC Regression Tests List				Total cases

Id	Functionality Group	Functionality	Functionality Summary
Bugs 1.1.4
REG_PLF304_SOC_001	Social	People	Check Use name instead of login for connection activities	1
REG_PLF304_SOC_002	Social	People	Check activities of connecting user	1
REG_PLF304_SOC_003	Social	People	Accepting invitation clears the list	1
Bugs 1.1.5
REG_PLF305_SOC_001	Social	Space	Check the displaying of space in My Space menu	1
REG_PLF305_SOC_002	Social	Space	Check activities when change date time	1
REG_PLF305_SOC_003	Social	People	Check the spelling in French message of connection request	1
REG_PLF305_SOC_004	Social	Space	Delete default application on space	1
REG_PLF305_SOC_005	Social	Space	Check avatar of admin in space	1
REG_PLF305_SOC_006	Social	Space	Check Space setting tab by user is non-moderator	1
REG_PLF305_SOC_007	Social	Space	Share link while add activity	1
Bugs 1.1.6
REG_PLF306_SOC_001	Social	People	Check activities after delete connection	1
REG_PLF306_SOC_002	Social	Space	Access space has the same name with page at the root path	2
Bugs 1.1.7
REG_PLF307_SOC_001	Social	Space		1
REG_PLF307_SOC_002	Social	Space		1
Bugs 1.1.8
REG_PLF308_SOC_001	Social	Space	Check View doc on a space	1
REG_PLF308_SOC_002	Social	Space	Check invite member whose name contains "-" to a private space	1
REG_PLF308_SOC_003	Social	Space	Check when sharing an activity within an empty activity stream	1
Bugs 1.1.8
REG_PLF309_SOC_001	Social	Space	Possible XSS attack by adding new activity stream	1
REG_PLF308_SOC_002	Social	Space	Check add a post or an answer that contains some characters	1
REG_PLF308_SOC_003	Social	Space	Check display in activity stream when click Like button	2
Total				15